## Instructions
Instructions-You do not need to include this instruction page in your Grants.gov application package.
This is an example of a work plan that includes some example reporting results that will be completed during end of year reporting. This is not the level of completion that will be expected for the application submission.
The workplan is a separate document from the text-based Project Narrative. It is a succinct overview of the program objectives, goals, activities, and projected outcomes in table format. The work plan is not a narrative. The work plan is organized by the Flex program areas and activity categories listed in the document Medicare Rural Hospital Flexibility Program Structure for FY 2024 - FY 2028. This is a work plan for FY24, or year 1, but it is intended to be a planning document for you to look forward to all 5 years, and document outcomes as such. FORHP does not expect you to have a completed plan for all 5 years. Only include the program areas and activity categories in the work plan that will be part of your state Flex Program. All other areas and activity categories should be removed from this work plan template prior to submission.
Note on color coding in the template: Quality Improvement = blue Financial and Operational = green Population Health = red EMS = orange CAH Designation=yellow
Work Plan Instructions: Below are definitions for each category of the work plan, for specific examples please reference the Flex Program Structure Document and the Flex Work Plan example.
https://www.ruralcenter.org/resources/flex-program-funding-guidance#fy24-structure
https://www.ruralcenter.org/resources/flex-program-funding-guidance#workplan-example
Activities Description: This is where you will provide the description of your QI activities and projects. An activity is a specific action taken to produce a result, but that may not always be able to measure an outcome. Activities can include things such as your needs assessment, networking meetings, one-time webinars, reporting support, and report and information dissemination. Projects are the more in-depth activities or a series of activities that will have associated outcomes. Such as a learning collaborative, an educational cohort, etc. In the description you can denote if activities/projects will span multiple years.
Program Area Impact Goal: The impact is the result or effect that is attributed to a project or program. Impact is often used to refer to higher level effects of a program that occur in the intermediate or long-term and can be intended or unintended, positive or negative. Your impact goal for QI might be, "demonstrably improve the care provided by the state's CAHs"
Project Type: The project type is a dropdown box for you to choose the overarching theme of the activity or project. For QI you can choose from the following. As a reminder, a project is different than an activity, and should have a defined and measurable outcome. For more examples on outcomes and definitions, reference the Flex Program Structure document and the Flex Program Glossary of Terms.
Expected Outputs: Measures that an activity occurred, stepping stones used to move forward. Examples include number of meetings, education programs, webinars provided. When completing your application you will fill out the outputs you are expecting, for example "All 15 CAHs will receive MBQIP reports" or "5 CAHs will receive HCAHPS training".
Actual Outputs: This is where you will report the actual outputs from the activity, for example, "All 15 CAHs received MBQIP reports" or "3 CAHs participated in HCAHPS training". This section will only be completed during progress reporting.
Staff Responsible: This is where you will denote who the main party responsible for carrying out the activity or project will be. For example, it could be the Flex Coordinator, or the Flex Coordinator and the Hospital Association. It might be subject to change later on and that's okay.
Engagement Impact: This section will only be completed during progress reporting. This is where you will talk about the qualitative outcomes, it's a chance to tell the story of the activity or project. You might say something like "The hospitals left the training indicating they felt much more prepared to report SDOH measures" or "the hospitals reported that patients said they were sleeping much better since efforts to improve quietness at night had been implemented".
Outcomes: Defined as a measurable change resulting from an activity or series of activities. Outcomes can be short-term, intermediate, and long-term. You might not have short, intermediate AND long-term outcomes, you might only have short term, or maybe you don't have two different intermediate outcomes and only have one. These are all acceptable scenarios. You will notice that for some of the activities you will not have associated outcomes, only the true projects will have related outcomes, where something like "report dissemination" will not.
In the outcome tracking section you will have a box to identify your goal and your result, these do not have to be completed at the time of application submission. The goal is what you are trying to achieve through a project; an achievable outcome that is generally broad and long-term. It will be your overall outcome goal for either your short-term, intermediate, or long-term outcomes. You can see examples of these in the work plan example document and you can find outcomes for each program area in the Flex Program Structure document.
Facility Tracking: Within the project section you will notice a facility tracking piece. This can be utilized to track the progress of participating facilities. You can find examples of how to complete this section in the Flex work plan example but this will only need to be completed during progress reporting. If you know any of this information at the time of submission you can certainly include it, but it is not required. If you need to add more facilities you can left click on one the facility rows and insert additional rows. Within the tracking piece you can indicate what their chosen outcome(s) will be, what their current baseline for that outcome(s) is, what their goal is, and at the end of the project you can document their result. Feel free to include notes about the project in the outcome tracking piece. You will notice a change in the column titles to track outcomes,
Expected outcomes from your CAH Quality Assessment and Inventory: In the QI tab you will see a box for "Expected outcomes from your CAH Quality Assessment and Inventory", this is for you to denote things you expect to see on your state's CAH Quality Assessment and Inventory survey, it might include predictions like "We anticipate there will be an identified need for continued health equity training and support as well as opportunities to educate on other models of care (community paramedicine, CHWs)". Although this information may play a role in your overall QI assessment, the intent of gathering this information is not to replace or indicate outcomes from your overall assessment.
Complete for Progress Reporting Only: When you see this on the work plan, it means this information field is not required for you to complete until you are providing updates on your work plan during end of year reporting. It does not have to be completed at the time of your application submission.
Please reference the Flex Program Glossary of Evaluation Terms for further clarification and guidance on included terminology. https://www.ruralcenter.org/resources/core-competency-managing-information-and-evaluation#eval-terms

## Example-Quality Improvement
Activities Description | Project Type | Expected Outputs | Actual Outputs (complete for progress reporting only) | Staff Responsible | Engagement Impact (complete for progress reporting only) | Short-term Expected Outcomes Effects occurring more immediately, typically within the first year | Intermediate Expected Outcomes Effects that occur in the first 1-2 years | Intermediate Expected Outcomes Effects that occur in the first 1-2 years | Long-term Expected Outcomes Effects that occur after 3 years | Long-term Expected Outcomes Effects that occur after 3 years
Program Area 1: Critical Access Hospital (CAH) Quality Improvement (a minimum of one activity is required)
Program Area Impact Goal: Demonstrably improve the quality of care in the state's CAHs
Quality Improvement Needs Assessment (required) | [5 empty] | We anticipate there will be an identified need for continued health equity training and support as well as opportunities to educate on other models of care (community paramedicine, CHWs)
A statewide needs assessment will be conducted | Quality Improvement Assessment | 1 needs assessment will be completed |  | Flex Coordinator
Quality Improvement Education (information dissemination, meetings)
Host 2 webinars to assist CAHs with development of strategies to collect SDOH data | SDOH | 10/15 CAHs will begin reporting SDOH data on time |  | Flex Coordinator/QI SME
Quality Improvement Education (information dissemination, meetings)
Conduct an educational webinar to ensure all health care providers and eligible patient populations receive their influenza vaccinations | Immunization | Number of CAHs who attend and or receive meeting notes and resources for each quarterly quality meeting |  | Flex Coordinator/QI SME
Quality Measure Reporting Support | [5 empty] | Short-term Outcome Description
Provide 1:1 TA to facilities on reporting questions and quality improvement opportunities | MBQIP Reporting | Number of TA requests, 15 expected |  | Flex Coordinator/QI SME |  | Goal: Increase the # of CAHs reporting all MBQIP measures by 3 CAHs (currently 12 CAHS) Overall Result:
Quality Improvement Project | [5 empty] | Short-term Outcome Description | Intermediate Outcome Description | Intermediate Outcome Description | Long-term Outcome Description | Long-term Outcome Description
Create a cohort of CAHs not currently meeting the EDTC MBQIP benchmark for EDTC (100%), and work with them to assess strategies for improving their EDTC measure performance (2 year project) | EDTC | Conduct bi-monthly cohort meetings (6) with CAHs to discuss implementation strategies; Tracking and review of EDTC data for previous quarters |  | Flex Coordinator/QI SME |  | Goal: # of hospitals identifying and implementing a standardized process for documentation & transfer of information to next care setting Overall Result: | Goal: Increase in number of hospitals reaching 100% benchmark for EDTC measure, and continued improvement in EDTC measure % for hospitals not yet attaining benchmark. Overall Result: | Goal: Overall Result: | Goal: Overall Result: | Goal: Overall Result:
Facility Tracking (complete for progress reporting only) |  | Outcome(s) | Baseline | Goal | Result | Notes: | Notes: | Notes: | Notes: | Notes:
Crestview General Hospital |  | Improvement in rate of performance for all EDTC components (EDTC-ALL) & Improvement in rate of performance for Medications Administered in ED | 65% | 100%
Sunridge Memorial Hospital |  | Improvement in rate of performance for Mental Status/Orientation Assessment | 52% | 100%
Lakeside Hospital |  | Improvement in rate of performance for Tests and/or Procedures Performed | 40% | 100%
Summit Peak Hospital |  | Improvement in rate of performance for Tests and/or Procedures Performed | 80% | 100%
Oakwood Community Hospital |  | Improvement in rate of performance for ED Provider Note | 39% | 100%
Meadowbrook Memorial Hospital |  | Improvement in rate of performance for Home Medications | 50% | 100%

## Example-Financial & Operational
Activities Description | Project Type | Expected Outputs | Actual Outputs (complete for progress reporting only) | Staff Responsible | Engagement Impact (complete for progress reporting only) | Short-term Expected Outcomes Effects occurring more immediately, typically within the first year | Intermediate Expected Outcomes Effects that occur in the first 1-2 years | Intermediate Expected Outcomes Effects that occur in the first 1-2 years | Long-term Expected Outcomes Effects that occur after 3 years | Long-term Expected Outcomes Effects that occur after 3 years
Program Area 2: CAH Financial and Operational Improvement (a minimum of one activity is required)
Program Area Impact Goal: 5 CAHs fall off the vulnerable hospital list
Assessment (statewide or individual) | [5 empty] | We anticipate there will be an identified need for 4 vulnerable hospitals to receive chargemaster reviews and a project focused on reducing claim denials for all CAHs.
A statewide needs assessment will be conducted | Statewide Financial and Operational Assessment | 1 needs assessment will be completed |  | Flex Coordinator
Education (information dissemination, meetings)
Disseminate CAHMPAS financial info to CAHs | General Education | All 15 CAHs will receive their info |  | Flex Coordinator
CAH Financial and Operational Improvement Project | [5 empty] | Short-term Outcome Description | Intermediate Outcome Description | Intermediate Outcome Description | Long-term Outcome Description | Long-term Outcome Description
Fund chargemaster reviews for 4 CAHs to identify and correct errors in list of procedures and related codes/charges, and work with the CAHs as a cohort to implement changes | Chargemaster Review | 4 CAHs will receive a chargemaster review and corresponding improvement plan |  | Flex Coordinator/F&O SME |  | Goal: 100% of CAHs identify changes needed to their chargemaster Overall Result: | Goal: Improved net revenue per adjusted admission Overall Result: | Goal: Improved net revenue per adjusted admission Overall Result: | Goal: Improved net revenue per adjusted admission Overall Result: | Goal: Improved operating margin (CAHMPAS) Overall Result:
Facility Tracking (complete for progress reporting only) |  | Baseline | Goal | Facility Lead | Result | Notes: | Notes: | Notes: | Notes: | Notes:
Crestview General Hospital |  | 20% of claims denied | Reduce errors by 75% | Mary P.
Lakeside Hospital |  | 5% of claims denied | Reduce errors by 75% | John S.
Summit Peak Hospital |  | 9% of claims denied | Reduce errors by 75% | Jason W.
Oakwood Community Hospital |  | 7% of claims denied | Reduce errors by 75% | Tabitha L.
CAH Financial and Operational Improvement Project | [5 empty] | Short-term Outcome Description | Intermediate Outcome Description | Intermediate Outcome Description | Long-term Outcome Description | Long-term Outcome Description
Provide a billing and coding training open to all 15 CAHs | Billing and Coding Education | 5/15 CAHs will attend the training |  | Flex Coordinator/F&O SME |  | Goal: 100% of CAHs identify changes needed to coding and billing systems Overall Result: | Goal: Reduced percentage of claims denied Overall Result: | Goal: Increase percentage of denied claims re-billed Overall Result: | Goal: Improved clean claims rate Overall Result: | Goal: Improved days in net revenue in accounts receivable (CAHMPAS) Overall Result:
Facility Tracking (complete for progress reporting only) |  | Baseline | Goal | Facility Lead | Result | Notes: | Notes: | Notes: | Notes: | Notes:
Crestview General Hospital |  | 20% of claims denied | Reduce errors by 75% | Mary P.
Lakeside Hospital |  | 5% of claims denied | Reduce errors by 75% | John S.
Summit Peak Hospital |  | 9% of claims denied | Reduce errors by 75% | Jason W.
Oakwood Community Hospital |  | 7% of claims denied | Reduce errors by 75% | Tabitha L.
CAH Financial and Operational Improvement Project | [5 empty] | Short-term Outcome Description | Intermediate Outcome Description | Intermediate Outcome Description | Long-term Outcome Description | Long-term Outcome Description
A cohort of CAHs engaged in a Flex-sponsored learning collaborative has implemented a project to reduce denied claims and improve collections from patients and third-party payers | Revenue Cycle Management | 5/15 CAHs will participate in the cohort |  | Flex Coordinator & Hospital Association |  | Goal: Reduced registration errors as a percent of total registrations Overall Result: | Goal: Reduced percentage of claims denied Overall Result: | Goal: Improved clean claims rate Overall Result: | Goal: Increase percentage of denied claims re-billed Overall Result: | Goal: Improved days’ net revenue in accounts receivable (CAHMPAS) Overall Result:
Facility Tracking (complete for progress reporting only) |  | Baseline | Goal | Facility Lead | Result | Notes: We will be gathering the # and % of errors at the beginning of the cohort. | Notes: | Notes: | Notes: | Notes:
Riverside Hospital |  | Unknown at this time | 50% reduction in registration errors | Jacob M.
Pinecrest Hospital |  | Unknown at this time | 50% reduction in registration errors | Bobby C.
Sunridge Memorial Hospital |  | Unknown at this time | 50% reduction in registration errors | Teresa K.
Willowbrook General Hospital |  | Unknown at this time | 50% reduction in registration errors | Lois H.
Brookside Medical Center |  | Unknown at this time | 50% reduction in registration errors | Barbara F.

## Example-Population Health
Activities Description | Project Type | Expected Outputs | Actual Outputs (complete for progress reporting only) | Staff Responsible | Engagement Impact (complete for progress reporting only) | Short-term Expected Outcomes Effects occurring more immediately, typically within the first year | Intermediate Expected Outcomes Effects that occur in the first 1-2 years | Intermediate Expected Outcomes Effects that occur in the first 1-2 years | Long-term Expected Outcomes Effects that occur after 3 years | Long-term Expected Outcomes Effects that occur after 3 years
Program Area 3: CAH Population Health (optional)
Program Area Impact Goal: Build capacity of CAHs to achieve measurable improvements in the health outcomes of their communities
Needs Assessment (individual or statewide) | [5 empty] | We anticipate there will be a need to focus on chronic care management as our state has seen a 10% increase in the rate of diabetes over the past 5 years.
A statewide needs assessment will be conducted | Statewide Population Health Assessment | 1 needs assessment will be completed |  | Flex Coordinator
Education (information dissemination, meetings)
Provide training to non-profit CAHs to understand IRS reporting requirements and best practices for a comprehensive CHNA. | Community Engagement | 15 CAHs will attend the training |  | Flex Coordinator and Pop Health SME
Population Health Project | [5 empty] | Short-term Outcome Description | Intermediate Outcome Description | Intermediate Outcome Description | Long-term Outcome Description | Long-term Outcome Description
Hold strategic planning events for up to 6 CAHs at 2 events to determine priority areas and action steps to improve implementing a chronic care management program after reviewing the summary brief findings on diabetes. | Chronic Care Management | 6 CAHs will attend 2 events |  | Flex Coordinator and CCM SME |  | Goal: # and % of CAHs that have implemented a patient registry for one or more chronic conditions Overall Result: | Goal: # and % of diabetic patients registered in CCM program Overall Result: | Goal: Reduction in the # and % of patients with poor control of daily blood glucose level Overall Result: | Goal: Reduction in the # and % of prediabetic patients developing Type 2 diabetes Overall Result: | Goal: Reduction in rate of unnecessary hospital admissions due to complications of diabetes (for participating patients) Overall Result:
Facility Tracking (complete for progress reporting only) |  | Baseline | Goal | Facility Lead | Result | Notes: We will be choosing participating hospitals during the first quarter of FY24 | Notes: | Notes: | Notes: | Notes:
TBD
TBD
TBD
TBD
TBD
TBD

## Example-EMS
Activities Description | Project Type | Expected Outputs | Actual Outputs (complete for progress reporting only) | Staff Responsible | Engagement Impact (complete for progress reporting only) | Short-term Expected Outcomes Effects occurring more immediately, typically within the first year | Intermediate Expected Outcomes Effects that occur in the first 1-2 years | Intermediate Expected Outcomes Effects that occur in the first 1-2 years | Long-term Expected Outcomes Effects that occur after 3 years | Long-term Expected Outcomes Effects that occur after 3 years
Program Area 4: Rural Emergency Medical Services (EMS) Improvement (optional)
Program Area Impact Goal: Improve the organizational capacity of rural EMS
Assessment (statewide or individual) and action planning | [5 empty] | We anticipate there will be an identified need to provide financial education to our state's rural EMS agencies.
A statewide needs assessment will be conducted | Statewide EMS Assessment | 1 needs assessment will be completed |  | Flex Coordinator
Education (information dissemination, meetings)
Provide Stop the Bleed training to rural EMS agencies. | Staff Education | 12 of 32 rural EMS agencies will complete Stop the Bleed training |  | Flex Coordinator and Stop the Bleed trainer
EMS Project | [5 empty] | Short-term Outcome Description | Intermediate Outcome Description | Intermediate Outcome Description | Long-term Outcome Description | Long-term Outcome Description
4-part training to improve billing and coding capacity for rural EMS agencies. | Financial Improvement | 5 of 32 rural EMS agencies will participate. |  | Flex Coordinator and billing and coding SME |  | Goal: # and % of agencies with appropriate billing and collection capacity Overall Result: | Goal: % reduction in time of processing claims Overall Result: | Goal: % reduction in days to collection Overall Result: | Goal: % reduction in registration errors as a percent of total registrations (total registration errors/total registrations) Overall Result: | Goal: # and % of EMS agencies with improved financial stability based on key financial indicators: • Improvement in the % of expenses covered by patient/transport revenues • Reductions in the % of expenses covered by other revenue sources (e.g., local tax revenues, grants, revenues) Overall Result:
Facility Tracking (complete for progress reporting only) |  | Baseline | Goal | Facility Lead | Result | Notes: | Notes: | Notes: | Notes: | Notes:
Facility 1
Facility 2
Facility 3
Facility 4
Facility 5

## Example-CAH Designation
Activities Description | Project Type | Expected Outputs | Actual Outputs (complete for progress reporting only) | Staff Responsible | Engagement Impact (complete for progress reporting only)
Program Area 6: CAH Designation (required if requested)
Program Area Impact Goal: Support rural hospitals who want to seek or maintain appropriate Medicare participation status to meet community needs
CAH Conversions and Transitions
Provide assistance to rural hospitals considering CAH designation through feasibility studies and providing information about the designation process. | CAH Conversion | Number of hospitals requesting information, 3 expected |  | Flex Coordinator
As required by the program authorizing legislation, State Flex Programs must assist with appropriate conversion of small rural hospitals to CAH status when requested. Flex programs must assist hospitals in evaluating the effects of conversion to CAH status.
This may include assisting with financial feasibility studies for hospitals considering conversion to CAH status (CAH Conversion) as well as feasibility studies for reopening closed rural hospitals or converting CAHs to other types of facilities (CAH Transition). There are no outcomes to report for this program area, only outputs.