## Instructions
PIMS Data Collection Tool
Version 4.0 (revised FY22)
This Excel workbook is an optional PIMS data collection tool for Flex Programs
The purpose of this tool is to facilitate data collection to enable easy and accurate reporting of PIMS measures at the end of the grant budget year. The tool tracks both planning and results of Flex-funded performance improvement projects. The tool is organized by activity categories and aligns with the questions asked in PIMS This data collection tool is designed to collect participation and improvement data over one grant year. Every activity category is listed in the financial tracking sheet and PIMS spending reports should include information about spending in every funded category whether or not CAH participation information is collected for that activity category. All State Flex Programs should use the financial spending report worksheet for calculating PIMS-reported spending.
Instructions by section
Quality Improvement
Fill in this page with the list of CAHs in your state.
Operational & Financial Improvement
Fill in this page with the list of CAHs in your state.
Population Health Improvement
Fill in this page with the list of CAHs in your state.
Emergency Medical Services Improvement
Fill in this page with a list of EMS Entitites particiapting in Flex actitivites in your state **note this should not include EMS supplement activiites**
Innovative Models
Fill in this page with the list of CAHs in your state.
CAH Conversion
Fill in this page with a list of hospitals that ask about CAH conversion assistance and receive some form of assistance whether or not they convert to CAHs.
Financial Spending Report
Use this worksheet to calculate how your total grant award should be attributed to the activity categories reported in PIMS. This will improve consistency in how different programs report spending.
Definitions
CAH (or EMS agency) participation is any engagement in a Flex-funded activity intended to improve a specific outcome for the CAH. All activities that count as participation should occur during the grant year for the current report. Activities may be multi-year, in which case the CAH will have participation for multiple years of PIMS reports.
Participation answers the question, “Did this entity engage in a Flex-funded activity intended to improve a specific outcome during the past grant year?”
CAH improvement is any change in the positive direction. Indicate improvement in the reporting cycle when it is identified. Some activities may not have data immediately available to assess improvement.
Improvement answers the question, “Did the participating CAH improve the outcome that was the target of the activity?”
Data sources for assessing improvement include: Self-report by the CAH State collected data MBQIP reports Flex Monitoring Team reports Other data sources as appropriate to specific projects Some data sources will be more timely and allow identification of improvement sooner than others. Additionally some types of activities will require a specific data source. For example only the CAH will be able to report and improvement in nurse staffing efficiency as a result of a nursing department performance improvement project.
EMS Entity - an EMS agency or ambulance service
Resources
This webinar playback focuses on PIMS from August 23, 2023
https://www.ruralcenter.org/events/flex-fiscal-year-fy-2022-wrap
A recorded video walk through of this tool is available as well.
https://www.ruralcenter.org/news-events/events/flex-pims-updates
Copies of the Flex program guidance are available on the TASC webpage.
https://www.ruralcenter.org/resources/flex-program-funding-guidance
Please post comments or questions about this tool in the Flex Program Forum or send to tasc@ruralcenter.org.
Update history
Version 1.0 released 5/24/2017
Version 1.1 released 8/2/2017 - formatting improvements and heading clarifications
Version 1.2 released 10/9/2018 - correction to total formula in Column D of spending calculator
Version 2.0 released 00/00/2019 - updated to reflect cooperative agreement changes and categories
Version 3.0 released 9/2021 - updated to reflect current program year
Version 4.0 released 10/2023 - updated to reflect FY22 dates, updated resource hyperlinks
Note on A29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nicole Clement what should we do with these areas?

## Quality Improvement
Program Area 1: Critical Access Hospital (CAH) Quality Improvement (Required)
| work plan category -->> |  | 1.1 Report and improve Core Patient Safety/Inpatient Measures, including develop antibiotic stewardship programs (required) | [6 empty] | 1.2 Report and improve Core Patient Engagment Measures (required) | [6 empty] | 1.3 Report and improve Core Care Transitions Measures (required) | [6 empty] | 1.4 Report and improve Core Outpatient Measures (required) | [6 empty] | 1.5 Report and Improve Additional Patient Safety Measures | [6 empty] | 1.6 Report and improve Additional Patient Engagement Measures | [6 empty] | 1.7 Report and improve Additional Care Transitions Measures | [6 empty] | 1.8 Report and improve Additional Outpatient Measures
CMS Number | Facility Name | Facility City | Participated in activity? | Baseline score (+ date) | Target | Start date | End date | Score after end | Improvement? | Participated in activity? | Baseline score (+ date) | target | Start date | End date | Score after end | Improvement? | Participated in activity? | Baseline score (+ date) | Target | Start date | End date | Score after end | Improvement? | Participated in activity? | Baseline score (+ date) | Target | Start date | End date | Score after end | Improvement? | Participated in measure activities? | Baseline score (+ date) | Target | Start date | End date | Score after end | Improvement? | Participated in measures activity? | Baseline score (+ date) | Target | Start date | End date | Score after end | Improvement? | Participated in measures activity? | Baseline score (+ date) | Target | Start date | End date | Score after end | Improvement? | Participated in measures activity? | Baseline score (+ date) | Target | Start date | End date | Score after end | Improvement?
Instructions on this page: This page tracks information for PIMS reporting on Quality Improvement activities of the state Flex program. This is a shortened page with example data. When entering your own state data start with the blank template which has 100 rows to list CAHs. Copy and paste your current state CAH list in the first columns on this page. CMS number and facility city are included for easy identification in the case of ambiguous names. For the quality measures with multiple components, such as EDTC and HCAHPS, a CAH may be working on one component or several as the target of an improvement project. Use whatever score composite, element, or elements makes the most sense in the context of that CAH's improvement project. Up-front identification of improvement targets with participating CAHs will make it easier to identify the right measures to monitor and assess for improvement. Example vignette for OP-27 performance improvement activities: -Two CAHs (A & D) are working to improve staff influenza vaccination rates for the 2016-2017 flu season. Their baselines are their OP-27 vaccination rates for the 2015-2016 flu season. -Three CAHs (B, E, & F) is not working on any Flex-funded improvement project. The CAH may be reporting OP-27 for MBQIP but they aren't participating in a Flex-funded improvement project so they are not reported for PIMS participation. -One CAH (C) is did not report OP-27 for the 2015-2016 flu season and their improvement project is to start reporting this year. -As part of the improvement project, the three participating CAHs are reporting their OP-27 rates directly to their Flex coordinator as well as reporting through NHSN. Therefore the Flex coordinator can assess project results and identify which CAHs improved before the MBQIP reports come out. (Note that OP-27 is usually published by the end of August so MBQIP reports would also be available before the PIMS due date in this case.) -One of the CAHs (D) had no change in OP-27 vaccination rates for the flu season so no improvement is reported for that CAH in PIMS. The other two increased their OP-27 rates above their baselines so they are reported as showing improvement for this budget year. Since these are one-year rapid cycle improvement projects, the Flex coordinator will reassess participation and which CAHs to track for FY 17 PIMS reporting.

## Operational & Financial Improve
Program Area 2: CAH Operational and Financial Improvement (required)
| work plan category -->> |  | 2.1 Statewide operation and financial needs assessment (required) |  | 2.2 Individual CAH specific needs assessment and action planning | [6 empty] | 2.3 Financial improvement | [6 empty] | 2.4 Operational Improvement | [6 empty] | 2.5 Value-based payment projects
CMS Number | Facility Name | Facility City | Participate in In-Depth Assessments? | Date Assessment Completed | Participate in Assessment? | Baseline indicator (+ date) | Indicator target | Indicator Improvement start date | Indicator Improvement end date | Indicator after end | Improvement on identified indicator(s)? | Participated in activity? | Baseline score (+ date) | Target | Start date | End date | Score after end | Improvement? | Participated in Operational Improvements activity? | Operational Improvements baseline data (+ date) | Operational Improvements target | Operational Improvements start date | Operational Improvements end date | Operational Improvements data after end | Improvement? | Participated in Value-based payment activity? | Value-based payment baseline data (+ date) | Value-based payment target | Start date | End date | Value-based Payment data after end | Improvement?
Instructions on this page: This page tracks information for PIMS reporting on Financial and Operational Improvement activities of the state Flex program. This is a shortened page with example data. When entering your own state data start with the blank template which has 100 rows to list CAHs. Copy and paste your current state CAH list in the first columns on this page. CMS number and facility city are included for easy identification in the case of ambiguous names. The Flex Monitoring Team and the Critical Access Hospital Financial Leadership Summit have identified a number of key financial indicators for CAHs. For any individual performance improvement project financial measures with multiple components, such as EDTC and HCAHPS, a CAH may be working on one component or several as the target of an improvement project. Use whatever score composite, element, or elements makes the most sense in the context of that CAH's improvement project. Up-front identification of improvement targets with participating CAHs will make it easier to identify the right measures to monitor and assess for improvement. Example vignette: -Two CAHs (A & F) received Flex-funded in-depth assessments this budget year. This participation is shown in the first section along with the assessment completion date for tracking. -Of the two, only one (CAH A) identified a financial indicator for improvement as a result of the assessment so the others are all No for 2.02 part two. -CAH A targeted Days in Net Accounts Receivable as a key financial indicator for improvement. Their goal is to reach the CAH median of 52 days in AR, but for the last fiscal year they had 82 days in AR. Following the assessment in December, CAH A began working on improving billing processes and communication to reduce days in AR. They will calculate days in AR for their fiscal year ending 9/1/17 next September and report their results to their Flex Coordinator before the PIMS due date of October 31.

## Population Health Improvement
Program Area 3: CAH Population Health (optional)
| work plan category -->> |  | 3.1 Support CAHs identifying community and resource needs | [6 empty] | 3.2 Assist CAHs to build strategies to prioritize and address unmet needs of the community | [6 empty] | 3.3 Assist CAHs to engage with community stakeholders and public health experts and address specific health needs
CMS Number | Facility Name | Facility City | Participated in activity? | Baseline data (+ date) | Target | Start date | End date | Data after end | Improvement? | Participated in activity? | Baseline data (+ date) | Target | Start date | End date | Data after end | Improvement? | Participated in activity? | Baseline data (+ date) | Target | Start date | End date | Data after end | Improvement?
Instructions on this page: This page tracks information for PIMS reporting on Financial and Operational Network activities of the state Flex program, activity category 2.04 in core area 2 of the Flex grant. This is a shortened page with example data. When entering your own state data start with the blank template which has 100 rows to list CAHs. Grantees need to report the following information in PIMS for Network activities: -The number of Financial and Operational Networks active during the budget year -The CAHs that participated in one or more of these networks Copy and paste your current state CAH list in the first columns on this page. CMS number and facility city are included for easy identification in the case of ambiguous names. List the active Financial and Operational Networks in columns F through K, inserting columns as necessary. For convenience CAHs that don't participate in any networks can be listed in Column E. When reporting in PIMS any CAH participating in one or more of these networks will be listed as participating. Example vignette: -Three CAHs (A, B, & C) are working together in a financial learning network with quarterly meetings of CFOs and other finance staff. They have identified billing and collections as an area that all three need to improve and they are planning targeted staff training for next year. -Three CAHs (C, D, & F) are members of a network focused on operational improvement activities. They are currently working on department-level productivity benchmarks and Lean training to improve departmental productivity. -The Flex Coordinator will report two active networks for the budget period. -CAH C is participating in two networks. However it will only be selected once in PIMS because PIMS collects the names of all CAHs in one or more networks. -One CAH (E) is not part of any organized network.

## Emergency Medical Services Impr
Program Area 4: Rural Emergency Medical Services (EMS) Improvement (optional)
work plan category -->> |  | 4.1 Statewide rural EMS needs assessment and action planning | [6 empty] | 4.2 Community-level rural EMS assessments and action planning | [5 empty] | 4.3 EMS operational improvement | [6 empty] | 4.4 EMS quality improvement
EMS Entity | Facility City | Participated in activity? | Baseline score (+ date) | Target | Start date | End date | Score after end | Improvement? | Participating in Community-level rural EMS System Assessment? | Date community EMS assessment completed | Start date | End date | Score after end | Improvement? | Participated in EMS operational improvement Activities? | Baseline score (+ date) | Target | Start date | End date | Score after end | Improvement? | Participated in EMS quality improvement Activity? | Baseline score (+ date) | Target | Start date | End date | Score after end | Improvement?
Instructions on this page: This page tracks information for PIMS reporting on CAH participation in Population Health and EMS improvement projects, part of core area 3 of the Flex grant. Grantees need to report the following information in PIMS for CAH activities: -Number of CAHs participating in improvement activities -Number of CAHs participating in these activities that showed improvement -Number of CAHs participating in community EMS assessments (no improvement reported) This is a shortened page with example data. When entering your own state data start with the blank template which has 100 rows to list CAHs. Copy and paste your current state CAH list in the first columns on this page. CMS number and facility city are included for easy identification in the case of ambiguous names.

## Rural Innovative Model
Program Area 5: Innovative Model Development (optional)
| work plan category -->> |  | 5.1 Develop and test innovative models and publish report or documentation of the innovation | [7 empty] | 5.2 Develop and test CAH outpatient clinic quality (incl. CAH-owned RHCs) quality reporting and publish report or documentation
CMS Number | Facility Name | Facility City | Participated in Innovative Models of Care activity? | Innovative Models of Care baseline score (+ date) | Innovative Models of Care target | Innovative Models of Care start date | Innovative Models of Care end date | Innovative Models of Care score after end | Reports published or other documentation of innovation | Improvement? | Participated in outpatient clinic quality reporting activity? | Baseline score (+ date) | target | Start date | End date | Score after end | Reports published or other documentation of innovation | Improvement?
Instructions on this page: This page tracks information for PIMS reporting on CAH participation in Innovative Model activities, core area 5 of the Flex grant. This is a shortened page with example data. When entering your own state data start with the blank template which has 100 rows to list CAHs. Copy and paste your current state CAH list in the first columns on this page. CMS number and facility city are included for easy identification in the case of ambiguous names. Grantees need to report the following information in PIMS for innovative model activities: -CAH participation in an innovative model activity or activities -Any participating CAHs that improved on the outcome targeted by the innovative model activity Example vignette: Four CAHs, (A, B, C & F) are participating in an innovative model activity facilitated by their Flex program to improve patient outcomes during transitions between CAHs and other health care settings. They want to improve care outcomes by insuring appropriate post-discharge follow up with eligible patients. For the purpose of this project, the CAHs are monitoring the number of patients that have a post-discharge care coordination contact from the hospital to either the patient or their primary care provider within 7 days of discharge. Participating CAHs report their care coordination rates to their Flex coordinator at the end of every quarter. The four CAHs start this project with different levels of existing capacity. -A & C have active care coordination programs and their goal is to increase the number of patients and/or primary care providers who are contacted for post-discharge follow up. Both CAHs successfully increase they numbers of patients who get post-discharge contacts. CAH A exceeds their target while CAH C does not. Since both CAHs improved during the grant year, both are reported as Improvement in PIMS. -CAHs B & F did not have a care coordination program at the start of the project year. CAH B successfully started a program and initiated care coordination contacts that reached 5% of patients in June through August. CAH B's target was to start a program, so by conducting care coordination contacts for 5% of patients they met their target even though their contact rates are much lower than CAH A and CAH C. CAH B is reported as Improvement in PIMS. -CAH F was not able to get their care coordination program off the ground in the project year. CAH F did not meet its target and did not show improvement. Therefore CAH F is not reported as Improvement in PIMS. CAH F was engaged with the Flex program and the other partners in care coordination so CAH F is reported Participation in PIMS. -Two other CAHs, D & E, are not participating in the innovative care coordination project so they are not reported for Participation in PIMS.

## CAH Conversion
Designation of CAHs
work plan category -->> |  |  | 6.1 CAH conversions (required if requested) |  |  | 6.2 CAH transitions (required if requested)
CMS Number | Facility Name | Facility City | Requested CAH Designation Assistance? | Successfully converted + date | Current conversion status | Requested CAH Transition to another Designation? | Transition Date | Current transition status
xx0031 | Smith Medical Center | Smithtown | YES | No | conversion in process | xx1304 | 2018-10-12 | Still a CAH
xx0052 | Northern Rock Medical Center | Rocktown | YES | No | CAH application denied 1/15/23 | xx1305 | 2020-02-04 | waiting to review results of Financial analysis
xx0037 | Briar Memorial Hospital | Briartown | YES | No | assessing options
was xx0050, new xx1350 | St Thomas Allentown Hospital | Allentown | YES | Yes, approval letter 2/1/23 | Converted
xx0041 | Hilltop Hospital | Youngstown | YES | No | decided not to convert
Instructions on this page: This page tracks information for PIMS reporting on CAH conversion activities of the state Flex Program. CAH Conversion is program area 6 of the Flex Program, and grantees need to report the following information in PIMS: -Number of non-CAH hospitals requesting and receiving assistance -Any CAHs on the current state CAH list that are newly-converted -Number of hospitals that sought assistance but have not converted -Names of hospitals that sought assistance but have not converted Record the names of any non-CAH hospitals receiving CAH conversion assistance during the current budget year on this page. Update their status when significant changes occur and review to ensure current status is listed here before completing the annual PIMS report. Note that these are non-CAH hospitals (except for CAHs newly converted in the current budget year) so the list of hospital names will be different from the other sections of the PIMS data collection tool. Conversion assistance may range from initial feasibility studies to helping with the actual submission of the conversion request to CMS. In this made-up example both Briar and Hilltop hospitals requested assistance with feasibility studies and evaluating options but they did not prepare an application to CMS. Since they requested technical assistance from their state Flex Program they are counted in the number of hospitals (5) requesting assistance and they will also be included in the list that did not successfully convert. This provides information about how much conversion technical assistance Flex programs are offering to hospitals that don't ultimately convert to CAHs.
For this sheet, list the names of non-CAH hospitals requesting conversion assistance and track the status of those requests and conversion efforts. These names will not be the same as the CAH list on the other tabs.

## Financial Spending Report
Flex PIMS Spending Worksheet - 9/1/22-8/31/23 Reporting Period
List your Flex grant award amounts, any approved carryover, and any unspent funds in the light gray boxes below. Actual program spending for the year will calculate automatically. This sheet is locked to avoid any inadvertent changes to the formulas. Only the light colored cells in column B are open for data entry.
Total FY 2022 grant award (from first NOA for the year) | 1100
Total FY 2021 approved Carryover (from Carryover Approval NOA, issued Jan. - Apr. Enter 0 if none) | 50
Total FY 2022 unspent funds (this will be close to UOB amount, may be estimated if full accounting for UOB is not complete in Sep. / Oct. Enter 0 if none.) | 25
Actual program spending for 9/1/22 - 8/31/23 (should be close to FFR but may not match exactly if accounting not finalized in Sep. / Oct.) | 1125
List your actual program spending directly attributed to specific projects in the light cells in the Direct Spending column. The other columns will auto-calculate. Report the total spending per activity category from the final column (Total Flex Spending) in PIMS. For activity categories with no spending enter 0. This calculation will improve consistency of reporting among Flex grantees who have different ways of implementing Flex activities through contracts and staff services. All spending not specifically assigned to an activity category is allocated for the purpose of PIMS reporting. ***This amount should NOT include EMS Supplement funds***
Spending Allocation for Flex Program Areas for Measures | Direct Spending | % of Direct Spending | Other Spending | Total Flex Spending
Program Area 1: Quality Improvement (required)
Activity 1.1 Report and improve Core Patient Safety/Inpatient Measures, including develop antibiotic stewardship programs (required) |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 1.2 Report and improve Core Patient Engagement Measures (required) |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 1.3 Report and improve Core Care Transitions Measures (required) |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 1.4 Report and improve Core Outpatient Measures (required) |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 1.5 Report and improve Additional Patient Safety Measures (optional) |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 1.6 Report and improve Additional Patient Engagement Measures (optional) |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 1.7 Report and improve Additional Care Transitions Measures (optional) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Activity 1.8 Report and improve Additional Outpatient Measures (optional) | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Subtotal | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Program Area 2: CAH Operational and Financial Improvement (required)
Activity 2.1 Statewide operation and financial needs assessment (required) |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 2.2 Individual CAH-specific needs assessment and action planning (optional) |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 2.3 Financial improvement (optional) |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 2.4 Operational improvement (optional) |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 2.5 Value-based payment projects (optional) |  | #DIV/0! | #DIV/0! | #DIV/0!
Subtotal | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Program Area 3: CAH Population Health (optional)
Activity 3.1 Support CAHs identifying community and resource needs |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 3.2 Assist CAHs to build strategies to prioritize and address unmet needs of the community |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 3.3 Assist CAHs to engage with community stakeholders and public health experts and address specific health needs |  | #DIV/0! | #DIV/0! | #DIV/0!
Subtotal |  | #DIV/0! | #DIV/0! | #DIV/0!
Program Area 4: Rural Emergency Medical Services (EMS) Improvement (optional)
Activity 4.1 Statewide rural EMS needs assessment and action planning |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 4.2 Community-level rural EMS assessments and action planning |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 4.3 EMS operational improvement |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 4.4 EMS quality improvement |  | #DIV/0! | #DIV/0! | #DIV/0!
Subtotal | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Program Area 5: Innovative Model Development (Optional)
Activity 5.1 Develop and test innovative models and publish report or documentation of the innovation |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 5.2 Develop and test CAH outpatient clinic quality reporting and publish report or documentation |  | #DIV/0! | #DIV/0! | #DIV/0!
Subtotal | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Program Area 6: CAH Designation (required if requested)
Activity 6.1 CAH conversions |  | #DIV/0! | #DIV/0! | #DIV/0!
Activity 6.2 CAH transitions
Subtotal | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Total Flex Budget Allocation | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Thank you to John Gale and Andy Coburn of the Flex Monitoring Team for developing this spending allocation template. Password to protect the sheet is flex |  |  | 1125
Use the last column to report spending per activity in PIMS.
Enter your award amounts and spending in each category in this column.