## Example Grant Writing Checklist

| Name of Grant: | XYZ Grant |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Grant Release Date: | Aug 1, 2014 | Grant Due Date: |  | Sept 30, 2014 |  |
| Proposal Component | Person(s) Responsible | Draft Due Date | Final Due Date |  | Complete() |
| Register for D&B Number |  |  | Aug 1 (recommended immediately) |  |  |
| Register for Electronic Handbook (EHB) |  |  | Aug 1 (recommended immediately) |  |  |
| Statement of Need |  | Sept 1 (recommended 3 weeks prior to full grant compilation) | Sept 8 |  |  |
| Project Narrative, including: - Goals & objectives - Methodology - Work plan narrative - Work plan - Sustainability plan - Evaluation plan |  | Sept 1 (3 weeks) | Sept 8 |  |  |
| Budget Table |  | Sept 1 (3 weeks) | Sept 8 |  |  |
| Budget Narrative |  | Sept 1 (3 weeks) | Sept 8 |  |  |
| Organization information, including: - Qualifications |  | Sept 8 (recommended 2 weeks prior to full grant compilation) | Sept 15 |  |  |
| Appendices, including: - Staff plan and position descriptions - Biographical sketches/resumes - Letters of Support |  | Sept 8 (2 weeks) | Sept 15 |  |  |
| Abstract |  | Sept 8 (2 weeks) | Sept 15 |  |  |
| Grant Fully Compiled |  | Sept 22 | Sept 24 (complete ahead of time to allow time for final review) |  |  |
| Submit to EHB |  |  | Sept 26 (submit ahead of final due date in case of processing errors) |  |  |