## Instructions
Instructions
The work plan is a separate document from the text-based Project Narrative. It is a succinct
overview of the program objectives, goals, activities, and projected outcomes in table format. The
work plan is not a narrative. The work plan is organized by the Flex program areas and activity
categories listed in the document Medicare Rural Hospital Flexibility Program Structure for
FY 2019 - FY 2023.
Only include the program areas and activity categories in the work plan that will be part of
your state Flex Program. All other areas and activitiy categories should be removed from this
work plan template.
This document contains a blank template for the 5-year Period of Performance and the FY 2019
Performance Year.
5-year Period of Peformance - This section should include goal statement(s) for each program area;
1-3 clearly defined outcome measures for each program area with clear, time-based targets for each
outcome measure per program area; and a 5-year timeline indicating project timespan at a high
level. Please note that some projects will span all five years of the period of performance while others
will not. Upon submission of the NOFO application, your program will only report on baseline and
target outcome measures as well as the date or time period that the data element is from. Each
subsequent year your program will update the 5-Year Period of Performance work plan with outcome
measures from the year's activities.
FY 2019 Performance Year - This section of the work plan should include succint descriptions of
activities planned for each activity category; expected outputs (process measures) for each activity
category; timeline for activities with key milestones to track progress, identifying multi-year activities
as appropriate; staffing to identify responsible individuals for each activity including program staff and
contractors; and budget of funds allocated to each activity category.
In the FY 2019 progress report you will update the Actual Outputs section of this work plan and develop
future work plans for the upcoming performance year using the sheets for future years.
FY 2020 - 2023 Performance Year - These tabs should be used for future work plans in future
non-competing continuations and annual progress reports. These tabs should not be completed for your
initial cooperative agreement submission and should not be submitted in Grants.gov.
You do not need to include this instruction page in your Grants.gov application package.
Note on color coding in the template:
Quality = blue
Operations = green
Population Health = red
EMS = orange
Innovation = purple
CAH designation = yellow

## 5-year Period of Performance
Program Area 1: Critical Access Hospital (CAH) Quality Improvement (required)
Goals: 1) Increase the number of CAHs consistently reporting quality data, and 2) Improve the quality of care in CAHs.
Active |  |  | Timeline (years)
Not included |  |  | 9/19 - 8/20 | 9/20 - 8/21 | 9/21 - 8/22 | 9/22 - 8/23 | 9/23 - 8/24
Activity Categories |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
1.1 Report and improve Core Patient Safety/Inpatient Measures, including develop antibiotic stewardship programs (required) |  |  | Active | Active | Active | Active | Active
1.2 Report and improve Core Patient Engagement Measures (required) |  |  | Active | Active | Active | Active | Active
1.3 Report and improve Core Care Transitions Measures (required) |  |  | Active | Active | Active | Active | Active
1.4 Report and improve Core Outpatient Measures (required) |  |  | Active | Active | Active | Active | Active
1.5 Report and improve Additional Patient Safety Measures |  |  | Not included | Not included | Not included | Not included | Not included
1.6 Report and improve Additional Patient Engagement Measures |  |  | Not included | Not included | Not included | Not included | Not included
1.7 Report and improve Additional Care Transitions Measures |  |  | Not included | Not included | Not included | Not included | Not included
1.8 Report and improve Additional Outpatient Measures |  |  | Not included | Not included | Not included | Not included | Not included
Overall description of program area approach: | Build capacity for reporting all MBQIP core measures and focus improvement projects on measures where CAHs perform worse than the national average.
Outcome Measure Description | Baseline | Target | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
a. Concept: Number of CAHs reporting all MBQIP core measures for the previous year. Data source: Applicable reporting quarters for Flex eligibility (e.g. for March 2018 the quarters are 3Q16-2Q17 for most measures, 1Q17-4Q17 for EDTC) Data timing: Assessed in March Measure population: 50 CAHs in the state. | 5/50 CAHs (10%) | 40/50 CAHs (80%) | Actual values | Actual values | Actual values | Actual values | Actual values
Data period used for reporting in each performance year
| March 2018 | March 2023 | March 2019 | March 2020 | March 2021 | March 2022 | March 2023
b. Concept: Number of CAHs meeting all 7 antibiotic stewardship core measures Data source: Assessed by the NHSN survey for the previous calendar year. Data timing: Survey data avaible by April each year Measure population: The 50 CAHs in the state | Baseline | Target | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
| 10/50 CAHs (20%) | 50/50 CAHs (100%) | Actual values | Actual values | Actual values | Actual values | Actual values
Data period used for reporting in each performance year
| CY 2017 (available April 2018) | CY 2023 (available April 2024) | CY 2019 (available April 2020) | CY 2020 (available April 2021) | CY 2021 (available April 2022) | CY 2022 (available April 2023) | CY 2023 (available April 2024)
Program Area 2: CAH Operational and Financial Improvement (required)
Goal: Improve the financial viability of CAHs.
Active |  |  | Timeline (years)
Not included |  |  | 9/19 - 8/20 | 9/20 - 8/21 | 9/21 - 8/22 | 9/22 - 8/23 | 9/23 - 8/24
Activity Categories |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
2.1. Statewide operation and financial needs assessment (required) |  |  | Active | Active | Active | Active | Active
2.2. Individual CAH-specific needs assessment and action planning |  |  | Not included | Not included | Not included | Not included | Not included
2.3. Financial improvement |  |  | Not included | Not included | Not included | Not included | Not included
2.4. Operational improvement |  |  | Not included | Not included | Not included | Not included | Not included
2.5. Value-based payment projects |  |  | Not included | Not included | Not included | Not included | Not included
Overall description of program area approach: | Encourage CAHs to report financial data to QHi for more immediate assistance with financial improvement. Target assistance including consultations and group projects to CAHs with negative financial trends based on timely QHi data.
Outcome Measure Description | Baseline | Target | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
a. Concept: number of CAHs in the state with operating margins >0.9% each year. Data source: state financial report database Data timing: annual unaudited data for prior fiscal years available in March, e.g. March 2018 for fiscal years ending in 2017. Measure population: all 50 CAHs in the state | 8 | 20 | Actual values | Actual values | Actual values | Actual values | Actual values
Data period used for reporting in each performance year
| 2017 financials (available March 2018) | reach target by year 3 and maintain thereafter | 2018 financials (available March 2019) | 2019 financials (available March 2020) | 2020 financials (available March 2021) | 2021 financials (available March 2022) | 2022 financials (available March 2023)
Program Area 3: CAH Population Health Improvement (optional)
Goal: Build capacity of CAHs to achieve measurable improvements in the health outcomes of their communities
Active |  |  | Timeline (years)
Not included |  |  | 9/19 - 8/20 | 9/20 - 8/21 | 9/21 - 8/22 | 9/22 - 8/23 | 9/23 - 8/24
Activity Categories |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
3.1 Support CAHs identifying community and resource needs |  |  | Active | Active | Active | Active | Active
3.2 Assist CAHS to build strategies to prioritize and address unmet needs of the community |  |  | Active | Active | Active | Active | Active
3.3 Assist CAHs to engage with community stakeholders and public health experts and address specific health needs |  |  | Not included | Not included | Not included | Not included | Not included
Overall description of program area approach: | Determine collective issues and trends in population health management for small rural hospitals through a Population Helath Management Needs Assessment.
Outcome Measure Description | Baseline | Target | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
a. Concept: Flex funded activities provided to increase awareness of community health needs to improve population health Data source: CAH CHNAs Data timing: CAH CHNAs completion by December 2019 and again by December 2022, summary brief reported annually Measure population: All state CAHs | TBD based on review of CHNAs | TBD based on review of CHNAs | Actual values | Actual values | Actual values | Actual values | Actual values
Data period used for reporting in each performance year
| 2019-12-01 | 2024-12-01 | 2020-12-01 | 2021-12-01 | 2022-12-01 | 2023-12-01 | 2024-12-01
Program Area 4: Rural Emergency Medical Services (EMS) Improvement (optional)
Goal: Improve the organizational capacity of rural EMS and improve the quality of rural EMS
Active |  |  | Timeline (years)
Not included |  |  | 9/19 - 8/20 | 9/20 - 8/21 | 9/21 - 8/22 | 9/22 - 8/23 | 9/23 - 8/24
Activity Categories |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
4.1 Statewide rural EMS needs assessment and action planning |  |  | Active | Active | Active | Active | Active
4.2 Community-level rural EMS assessments and action planning |  |  | Not included | Not included | Not included | Not included | Not included
4.3 EMS operational improvement |  |  | Active | Active | Not included | Not included | Not included
4.4 EMS quality improvement |  |  | Not included | Not included | Not included | Not included | Not included
Overall description of program area approach: | Determine rural EMS needs and improve time critical diagnosis EMS system capacity.
Outcome Measure Description | Baseline | Target | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
a. Concept: Time Critical Diagnosis (TCD) patient outcomes in participating EMS service areas Data source: Reporting from pilot project participants Data timing: June 2020 Measure population: Rural EMS agencies and CAHs | 0/24 EMS agencies using AHA Lifeline guides for Stroke and STEMI | 67% of EMS agencies using guidelines | Actual values | n/a | n/a | n/a | n/a
Data period used for reporting in each performance year
| 2019-09-01 | 2021-06-01 | 2020-06-01
Program Area 5: Innovative Model Development (optional)
Goal: Increaase knowledge and evidence base supporting new models of rural health care delivery
Active |  |  | Timeline (years)
Not included |  |  | 9/19 - 8/20 | 9/20 - 8/21 | 9/21 - 8/22 | 9/22 - 8/23 | 9/23 - 8/24
Activity Categories |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
5.1 Develop and test innovative models and publish report or documentation of the innovation |  |  | Active | Active | Active | Not included | Not included
5.2 Develop and test CAH outpatient clinic quality reporting and publish report or documentation |  |  | Not included | Not included | Not included | Not included | Not included
Overall description of program area approach: | Develop, implement, and assess innovative health care models designed to have a positive transformational impact on rural health.
Outcome Measure Description | Baseline | Target | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
a. Concept: Creation of Statewide Telemedicine advisory group to identify barriers to development, share information and collaborate on best practices Data source: Provider, hospital and community feedback Data timing: Completed 8/31/20 Measure population: Statewide CAHs participating in telemedicine programming | no manual exists | manual created | Actual values | n/a | n/a | n/a | n/a
Data period used for reporting in each performance year
| 2019-09-01 | 2020-08-31 | 2020-08-01 | n/a | n/a | n/a | n/a
Outcome Measure Description | Baseline | Target | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
b. Concept: Increased access to care and patients remaining in their communities due to increase CAH participation in telemedicine Data source: Provider/hospital feedback Data timing: Assessing improvement in year 3; planning in year 1 and implementation in year 2 Measure population: Statewide CAHs participating in telemedicine programming | 3/50 CAHs in state using telemedicine | 12 CAHs using telemedicine | Actual values | Actual values | Actual values | n/a | n/a
Data period used for reporting in each performance year
| 2019-09-01 | 2022-08-01 | 2020-08-31 | 2021-08-31 | 2022-08-01 | n/a | n/a
Program Area 6: CAH Designation (required if requested)
Goal: Assist rural hospitals to seek or maintain appropriate Medicare participation status to meet community needs
Active |  |  | Timeline (years)
Not included |  |  | 9/19 - 8/20 | 9/20 - 8/21 | 9/21 - 8/22 | 9/22 - 8/23 | 9/23 - 8/24
Activity Categories |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
6.1 CAH conversions |  |  | Active | Active | Active | Active | Active
6.2 CAH transitions |  |  | Not included | Not included | Not included | Not included | Not included
Overall description of program area approach: | Assist remaining hospitals eligible for conversion with feasibility studies, the application process, preparation for the survey and CAH conversion.
Outcome Measure Description | Baseline | Target | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
a. Concept: Rural hospitals interested in conversion receive timely, accurate information about CAH designtation Data source: Documentation of services provided such as a feasibility study Data timing: Ongoing through award period Measure population: Remaining rural hospitals eligible for conversion | 3 eligible hospitals | Based on need of hospital, will provide TAS as requested | Actual values | Actual values | Actual values | Actual values | Actual values
Data period used for reporting in each performance year
| 2019-09-01 | 2024-08-31 | 2020-09-01 | 2021-09-01 | 2022-09-01 | 2023-09-01 | 2024-09-01

## FY 2019 Performance Year
Activities Description (by category) | Expected Outputs | Actual Outputs (complete for end of year report only) | Timeline and Key Milestones | Staffing
Program Area 1: Critical Access Hospital (CAH) Quality Improvement (required) |  |  | Total budget for program area: | 110000
1.1 Report and improve Core Patient Safety/Inpatient Measures (required annually) |  |  | Total budget for category: | 25000
Conduct an educational webinar to ensure all health care providers and eligible patient populations receive their influenza vaccinations | 50 CAHs who attend and or receive meeting notes and resources for each quarterly quality meeting. |  | 2020-08-31 | Flex Coordinator, SME
Provide 1:1 TA to facilities on reporting questions and quality improvement opportunities | Number of TA requests, 30 expected |  | Ongoing, as requested | Flex Coordinator
1.2 Report and improve Core Patient Engagement Measures (required annually) |  |  | Total budget for category: | 25000
Provide statewide HCAHPS data reports to 50 CAHs and identify high performers | Best practices shared quarterly with 50 CAHs |  | 12/1/2020, 3/1/2021, 6/1/2021, 8/31/2021 | Flex Coordinator
Improve CAH patient engagement through the use of HCAHPS and identify quality improvement activates and efforts for areas of improvement, leverage SHIP funding to support CAHs access to HCAHPS vendor | Conduct 5 HCAHPS focus groups at CAHs |  | Focus group planning and dates completed by 10/1/2019, focus groups completed by end of Q3 | Flex Coordinator, SME connected via phone for events
1.3 Report and improve Core Care Transitions Measures (required annually) |  |  | Total budget for category: | 35000
Collaborate with XX Quality Improvement Organization (QIO) to promote data collection, reporting and technical assistance to CAHs | 50/50 (100%) of CAHs report EDTC on time every quarter. |  | Completed by 5/31/20 | Flex Coordinator, QIO
1.4 Report and improve Core Outpatient Measures (required annually) |  |  | Total budget for category: | 25000
Host 2 webinars to assist CAHs with development of strategies to collect data internally and report nationally to the CMS hospital outpatient (OP) quality reporting program. | 40/50 (80%) CAHs reporting to the CMS hospital outpatient reporting program for the year |  | Webinars completed by end of Q1 | Flex Coordinator, SMEs
Program Area 2: CAH Operational and Financial Improvement (required) |  |  | Total budget for program area: | 100000
2.1 Statewide operational and financial needs assessments (required annually) |  |  | Total budget for category: | 100000
Disseminate CAHMPAS financial info to CAHs | 50 CAHs receive reports |  | 2019-11-01 | Flex Coordinator
Financial analysis using CAH cost reports is completed and used for presentations to CAHs, legislators and payors. | 1 presentation at statewide CAH meeting |  | Analysis completed by 6/1/20 | Flex Coordinator
Healthcare Indicator reports disseminated to all CAHs and used for presentation provided to CAHs, legislators and payors. | 50 CAHs receive reports, 1 presentation to legislators, 1 presentation to insurance companies |  | Report completed by 6/1/20 | Flex Coordinator
Hospital Association to conduct annual Salary Survey | Individual reports for each participating CAH |  | Survey completed by 2/1/20, report completed by 6/1/20 | Flex Coordinator, Hospital Association
Program Area 3: CAH Population Health Improvement (optional) |  |  | Total budget for program area: | 75000
3.1 Support CAHs identifying community and resource needs (optional) |  |  | Total budget for category: | 10000
Provide training to non-profit CAHs to understand IRS reporting requirements and best practices for a comprehensive CHNA. | 80% attendance of non-profit CAHs at training (32 CAHs expected) |  | Completed by 12/31/19 | Flex Coordinator
3.2 Assist CAHs to build strategies to prioritize and address unmet needs of the community (optional) |  |  | Total budget for category: | 65000
Put the CHNA, community benefits, and patient and family advisory council information summarized in the needs assessment into a summary brief to highlight needs and activities for rural and other state policy and programs leaders and then update annually. | Development of summary brief for rural communities, program leaders and state policymakers |  | Summary brief completed by 5/15/20 | Flex Coordinator, Hospital Association
Hold strategic planning events for up to 10 CAHs at 2 events to determine priority areas and action steps to improve community health based on summary brief findings | Strategic plans with action steps identified for 20 CAHs |  | Events held in Q3, strategic plans completed by 8/31/20 | Flex Coordinator, subcontractor
Program Area 4: Rural Emergency Medical Services (EMS) Improvement (optional) |  |  | Total budget for program area: | 60000
4.2 Community-level rural EMS assessments and action planning (optional) |  |  | Total budget for category: | 10000
Conduct community-level rural EMS needs assessment | Completion of 5 EMS needs assessments |  | Completed by 11/30/20 | Flex Coordinator, CAHs, EMS agencies
4.3 EMS operational improvement (optional) |  |  | Total budget for category: | 50000
Time Critical Diagnoses (TCD) patient management improvement pilot projects and best practices toolkit | 3 EMS agencies participate in pilot, toolkit published |  | Completed by 8/31/20 | Flex Coordinator, CAHs, EMS agencies
Program Area 5: Innovative Model Development (optional) |  |  | Total budget for program area: | 50000
5.1 Develop and test innovative models and publish report or documentation of the innovation (optional) |  |  | Total budget for category: | 50000
Facilitate Rural Statewide Telemedicine programming for advisory group to identify and address telemedicine barriers to development, share information and collaborate on best practices | Creation of advisory group and draft manual |  | Advisory group convene in FY 2019 with meetings in 1/20 and 5/20. Outline of manual completed by 7/31/20 | Flex Coordinator, subcontractor, regional telehealth resource center
Program Area 6: CAH Designation (required if requested) |  |  | Total budget for program area: | 10000
6.1 CAH conversions (required if assistance is requested by rural hospitals) |  |  | Total budget for category: | 10000
Provide assistance to rural hospitals considering CAH designation through feasibility studies and providing information about the designation process. | Number of hospitals requesting information, 3 exepcted |  | Ongoing as requested, activities completed by 8/31/20 | Flex Coordinator