## All tasks
Flex Monitoring Activities Worksheet
Timeline and Deliverables
Timetable and Deliverables
Task | Description | Cost | Date
1 | Contract and Sub-Contract Administration | $X,XXX/monthly | Monthly Upon Invoice
$XX,XXX total
WHA President and fiscal staff provide administrative oversight on the WCAHN Director’s sub-contract to ensure completion of all activities under this Amendment. WHA President and fiscal staff devote 10% of time to WCAHN activities.
2 | Sub-contract for WCAHN Director | $XX per hour Not to exceed $XX,XXX total | Monthly Upon Invoice
The WCAHN Director provides essential leadership and coordination necessary for the achievement of the WCAHN’s goals. WCAHN Director will direct and complete tasks 3-8 below as well as coordinate quarterly network meetings which will include educational sessions such as sessions on financial performance and quality improvement. WCAHN Director will: provide quarterly reports to the Office of Rural Health within 14 days of quarters end; provide an annual report to the Office of Rural Health by October 15, 2015; will input all completed activities into the National Organization of State Offices of Rural Health (NOSORH) Truserve performance measures tool within 14 days of activity completion; update WCAHN website; attend monthly flex group meetings; attend monthly one to one meetings; and prepare contract for subcontract awards which includes reporting of measures and outcomes per Flex grant guidelines.
Invoice shall include a breakdown of WCAHN Director’s activities conducted related to this Contract and activities listed must correspond to activities entered into the NOSORH TruServe performance measures tool.
3 | WCAHN Website Maintenance | Up to $X,XXX | Upon Invoice
Reimbursement of the web designer/host agency fees for maintaining the WCAHN website to ensure dissemination of information to WCAHN members and the public.
Invoice must include a copy of the web designer/host agency invoice.
Invoice must include a copy of the web designer/host agency invoice.
4 | Patient Safety Collaborative | Up to $X,XXX | Upon Invoice
Implement a patient safety collaborative that includes a survey and analysis, technical support, and educational components.
Invoice must include a copy of any sub-contractor/consultant’s invoice(s).
5 | Support for CAH Operational Improvement | Up to $XXX,XXX | Upon Invoice
Provide sub-recipient contracts for CAH Operational Improvement (e.g. LEAN, charge master review, revenue cycle improvement, onsite, quality coach, or other project specific QI initiative). The sub-recipient grants will be competitive and awardees will be selected by the Flex Coordinator, WCAHN Director, and Wyoming Hospital Association President based upon the needs of the CAH. Activity planning shall begin during Flex grant first quarter cycle; activities shall commence by Flex grant second quarter cycle.
Each sub-recipient must furnish Contractor with quarterly reports within 14 days of quarters end and Contractor must furnish each quarterly report to the Office of Rural Health as a section of the WCAHN quarterly report. Each sub-recipient must furnish Contractor with a final report by September 30, 2015, and Contractor must furnish the Office of Rural Health with each final report by October 15, 2015.
Invoice must include a breakdown of award, expenses, and must include a copy of sub-contractor/consultant's invoice(s).
6 | Sub-Contract with Kansas Hospital Education and Research Foundation | Up to $XX,XXX | Upon Invoice
Sub-contract with Kansas Hospital Education and Research Foundation (KHERF) to provide all Wyoming CAHs with continued access to Quality Health Indicators for benchmarking and quality improvement.
Invoice must include a copy of KHERF's invoice.
7 | Support for Financial and Operation Needs Assessment | Up to $XX,XXX | Upon Invoice
Provide sub-recipient contract for a financial and operational needs assessment for one CAH.
Sub-recipient must furnish Contractor with quarterly reports within 14 days of quarters end and Contractor must furnish each quarterly report to the Office of Rural Health as a section of the WCAHN quarterly report. Each sub-recipient must furnish Contractor with a final report by September 30, 2015, and Contractor must furnish the Office of Rural Health with each final report by October 15, 2015. Activity planning shall begin during Flex grant first quarter cycle; activities shall commence by Flex grant second quarter cycle.
Invoice must include a breakdown of expenses and must include a copy of the sub-contractor/consultant's invoice(s).
8 | WCAHN Member Conference Registration and Travel Scholarships | Up to $XX,XXX | Upon Invoice
Conference registration and travel scholarships available for CAH staff and board of directors to attend approved continuing education events, CAH-related conferences and trainings in order to keep abreast of best practices and current issues in healthcare affecting these facilities. Examples: National Rural Health Association’s Critical Access Hospital Conference, Annual Meeting, and Policy Institute; Western Region and National Flex conferences; Flex strategic planning meeting; etc. WCAHN Director will conduct post travel evaluations based on the criteria provided by the ORHP and Post-Test Only Model of Training Evaluation for Flex Grantees. Evaluations will be conducted within 7 days of travel completion. Evaluation results will be uploaded into TruServe within 14 days of travel completion. Evaluations must be received by WCAHN Director prior to CAH reimbursement. (This includes WCAHN quarterly meeting charges)
Invoice must include a breakdown of scholarships issued, total cost, maps to verify mileage reimbursed at the federal level, and copies of receipts submitted by recipients. All required travel documentation, per person, per trip, is to be submitted in one invoice.
TOTALS |  | $XXX,XXX

## Task 1
Task | Description |  | Cost | Date | Invoice Rec'd | Invoice Approved | Comments | Invoice Processed | Acct Paid
1 | Contract and Sub-Contract Administration | $X.XXX/monthly |  | Monthly Upon Invoice
$XX,XXX total
WHA President and fiscal staff provide administrative oversight on the WCAHN Director’s sub-contract to ensure completion of all activities under this Amendment. WHA President and fiscal staff devote 10% of time to WCAHN activities.
| For Month: | 0
September 2014
October 2014
November 2014
December 2014
January 2015
February 2015
March 2015
April 2015
May 2015
June 2015
July 2015
August 2015
| Remaining funds | 0 | 0

## Task 2
Timetable and Deliverables |  |  |  |  | Invoice Rec'd | Invoice Approved | Comments | TruServe Inputs | Invoice Processed
Task | Description |  | Cost | Date
2 | Sub-contract for WCAHN Director | $XX per hour - Not to exceed $XX,XXX total |  | Monthly Upon Invoice
The WCAHN Director provides essential leadership and coordination necessary for the achievement of the WCAHN’s goals. WCAHN Director will direct and complete tasks 3-8 below as well as coordinate quarterly network meetings which will include educational sessions such as sessions on financial performance and quality improvement. WCAHN Director will: provide quarterly reports to the Office of Rural Health within 14 days of quarters end; provide an annual report to the Office of Rural Health by October 15, 2015; will input all completed activities into the National Organization of State Offices of Rural Health (NOSORH) Truserve performance measures tool within 14 days of activity completion; update WCAHN website; attend monthly flex group meetings; attend monthly one to one meetings; and prepare contract for subcontract awards which includes reporting of measures and outcomes per Flex grant guidelines.
Invoice shall include a breakdown of WCAHN Director’s activities conducted related to this Amendment and activities listed must correspond to activities entered into the NOSORH TruServe performance measures tool.
Quarterly meetings scheduled
September 24. 2014
0
September 2014
October 2014
November 2014
December 2014
January 2015
February 2015
March 2015
April 2015
May 2015
June 2015
July 2015
August 2015
| Remaining funds | 0 | 0

## Task 3
Timetable and Deliverables |  |  |  |  | Invoice Rec'd | Invoice Approved | Comments | TruServe Inputs | Invoice Processed
Task | Description |  | Cost | Date
3 | WCAHN Website Maintenance | Up to $X,XXX |  | Upon Invoice
Reimbursement of the web designer/host agency fees for maintaining the WCAHN website to ensure dissemination of information to WCAHN members and the public.
Invoice must include a copy of the web designer/host agency invoice.
1200
| September 2014 |  | 100
October 2014
November 2014
December 2014
January 2015
February 2015
March 2015
April 2015
May 2015
June 2015
July 2015
August 2015
| Funds Remaining | -1100 | 100

## Task 4
Timetable and Deliverables |  |  |  |  | Invoice Rec'd | Invoice Approved | Comments | TruServe Inputs | Invoice Processed
Task | Description |  | Cost | Date
4 | Patient Safety Collaborative | Up to $X,XXX |  | Upon Invoice
Implement a patient safety collaborative that includes a survey and analysis, technical support, and educational components.
Invoice must include a copy of the sub-contractor/consultant’s invoice(s).
0
September 2014
October 2014
November 2014
December 2014
January 2015
February 2015
March 2015
April 2015
May 2015
June 2015
July 2015
August 2015
|  | 0 | 0

## Task 5
Timetable and Deliverables |  |  |  |  | Invoice Rec'd | Invoice Approved | Comments | TruServe Inputs | Invoice Processed
Task | Description |  | Cost | Date
5 | Support for CAH Operational Improvement | Up to $XXX,XXX |  | Upon Invoice
Provide sub-recipient contracts for CAH Operational Improvement (e.g. LEAN, charge master review, revenue cycle improvement, onsite, quality coach, or other project specific QI initiative). The sub-recipient grants will be competitive and awardees will be selected by the Flex Coordinator, WCAHN Director, and Wyoming Hospital Association President based upon the needs of the CAH. Activity planning shall begin during Flex grant first quarter cycle; activities shall commence by Flex grant second quarter cycle.
Each sub-recipient must furnish Contractor with quarterly reports within 14 days of quarters end and Contractor must furnish each quarterly report to the Office of Rural Health as a section of the WCAHN quarterly report. Each sub-recipient must furnish Contractor with a final report by September 30, 2015, and Contractor must furnish the Office of Rural Health with each final report by October 15, 2015.
Invoice must include a breakdown of award, expenses, and must include a copy of sub-contractor/consultant's invoice(s).
0
September 2014
October 2014
November 2014
December 2014
January 2015
February 2015
March 2015
April 2015
May 2015
June 2015
July 2015
August 2015
| Funds Remaining | 0 | 0
0

## Task 6
Timetable and Deliverables |  |  |  |  | Invoice Rec'd | Invoice Approved | Comments | TruServe Inputs | Invoice Processed
Task | Description |  | Cost | Date
6 | Sub-Contract with Kansas Hospital Education and Research Foundation | Up to $XX,XXX |  | Upon Invoice
Sub-contract with Kansas Hospital Education and Research Foundation (KHERF) to provide all Wyoming CAHs with continued access to Quality Health Indicators for benchmarking and quality improvement.
Invoice must include a copy of KHERF’s invoice.
0
September 2014
October 2014
November 2014
December 2014
January 2015
February 2015
March 2015
April 2015
May 2015
June 2015
July 2015
August 2015
0
| Funds remaining | 0

## Task 7
Timetable and Deliverables |  |  |  |  | Invoice Rec'd | Invoice Approved | Comments | TruServe Inputs | Invoice Processed
Task | Description |  | Cost | Date
7 | Support for Financial and Operation Needs Assessment | Up to $XX,XXX |  | Upon Invoice
Provide sub-recipient contract for a financial and operational needs assessment for one CAH. Sub-recipient must furnish Contractor with quarterly reports within 14 days of quarters end and Contractor must furnish each quarterly report to the Office of Rural Health as a section of the WCAHN quarterly report. Each sub-recipient must furnish Contractor with a final report by September 30, 2015, and Contractor must furnish the Office of Rural Health with each final report by October 15, 2015. Activity planning shall begin during Flex grant first quarter cycle; activities shall commence by Flex grant second quarter cycle. Invoice must include a breakdown of expenses and must include a copy of the sub-contractor/consultant's invoice(s).
0
September 2014
October 2014
November 2014
December 2014
January 2015
February 2015
March 2015
April 2015
May 2015
June 2015
July 2015
August 2015
| Funds Remaining | 0 | 0

## Task 8
Timetable and Deliverables |  |  |  |  | Invoice Rec'd | Invoice Approved | Comments | TruServe Inputs | Invoice Processed
Task | Description |  | Cost | Date
8 | WCAHN Member Conference Registration and Travel Scholarships | Up to $XX,XXX |  | Upon Invoice
Conference registration and travel scholarships available for CAH staff and board of directors to attend approved continuing education events, CAH-related conferences and trainings in order to keep abreast of best practices and current issues in healthcare affecting these facilities. Examples: National Rural Health Association’s Critical Access Hospital Conference, Annual Meeting, and Policy Institute; Western Region and National Flex conferences; Flex strategic planning meeting; etc. WCAHN Director will conduct post travel evaluations based on the criteria provided by the ORHP and Post-Test Only Model of Training Evaluation for Flex Grantees. Evaluations will be conducted within 7 days of travel completion. Evaluation results will be uploaded into TruServe within 14 days of travel completion. Evaluations must be received by WCAHN Director prior to CAH reimbursement. (This includes WCAHN quarterly meeting charges)
Invoice must include a breakdown of scholarships issued, total cost, maps to verify mileage reimbursed at the federal level, and copies of receipts submitted by recipients. All required travel documentation, per person, per trip, is to be submitted in one invoice.
0
September 2014
October 2014
November 2014
December 2014
January 2015
February 2015
March 2015
April 2015
May 2015
June 2015
July 2015
August 2015
| Funds Remaining | 0 | 0

## Task 9
Timetable and Deliverables |  |  |  |  | Invoice Rec'd | Invoice Approved | Comments | TruServe Inputs | Invoice Processed
Task | Description |  | Cost | Date
9
September 2014
October 2014
November 2014
December 2014
January 2015
February 2015
March 2015
April 2015
May 2015
June 2015
July 2015
August 2015
| Funds Remaining | 0 | 0

## Task 10
Timetable and Deliverables |  |  |  |  | Invoice Rec'd | Invoice Approved | Comments | TruServe Inputs | Invoice Processed
Task | Description |  | Cost | Date
10
September 2014
October 2014
November 2014
December 2014
January 2015
February 2015
March 2015
April 2015
May 2015
June 2015
July 2015
August 2015
| Funds Remaining | 0 | 0

## Task 11
Timetable and Deliverables |  |  |  |  | Invoice Rec'd | Invoice Approved | Comments | TruServe Inputs | Invoice Processed
Task | Description |  | Cost | Date
11
0
September 2014
October 2014
November 2014
December 2014
January 2015
February 2015
March 2015
April 2015
May 2015
June 2015
July 2015
August 2015
| Funds Remaining | 0 | 0

## Task 12
Timetable and Deliverables |  |  |  |  | Invoice Rec'd | Invoice Approved | Comments | TruServe Inputs | Invoice Processed
Task | Description |  | Cost | Date
10
0
September 2014
October 2014
November 2014
December 2014
January 2015
February 2015
March 2015
April 2015
May 2015
June 2015
July 2015
August 2015
| Funds Spent/Remaining | 0 | 0

## RHS
Timetable and Deliverables | Invoice Rec'd | Invoice Approved | Comments | TruServe Inputs | Invoice Processed

## EMS
Timetable and Deliverables |  | Invoice Rec'd | Invoice Approved | Comments | TruServe Inputs | Invoice Processed
0
September 2014
October 2014
November 2014
December 2014
January 2015
February 2015
March 2015
April 2015
May 2015
June 2015
July 2015
August 2015
Funds Remaining | 0 | 0