## Price Transparency
Hospital Name
Hospital Location | [5 empty] | Today
Price Transparency 2021 Work Plan | [5 empty] | 2020-10-19
Category | Task | Department | Responsible Party | Anticipated Completion Date | Revised/Actual Completion Date | Days to Complete | Status | Actions
High level task category | Specific task or work item required to be completed | Department Responsible for completion of task or reporting on the completion | Individual Responsible for completion of task or reporting on the completion | Target date for task completion | New date due to early completion or extended deadline | G= >5 days Y= 0-5 days R= Past Due | Any comments or note to explain revised expectation or delays | Use to document decisions made
Example Price Transparency Work Group | Populate the work plan | Price Transparency Work Group | Price Transparency Lead | 2020-08-15 | 2020-08-31 | -48 | Due to vacations we had to push this date out | Work Group established - members include:???, Charter established
Charges for Hospital Employed Physicians |  |  |  |  | 2020-11-01 | 12
Standard Charges
Negotiated payer specific charges/rates | [5 empty] | -43489
Cash Discounted Rates | [5 empty] | -43489
De-identified Minimum
De-identified Maximum
Pricing Policy and Strategy | [5 empty] | Completed
Shoppable Services | [5 empty] | -43489
Machine Readable Format | [5 empty] | -43489
Completed
Mark-Up formularies for any/all departments | [5 empty] | -43489
Covid Specific postings | [5 empty] | -43489
-43489
-43489