Critical Access Hospital Replacement Process:

The Roadmap

Table of Contents

Introduction	3

Critical Access Hospital Replacement Process Timeline	5

Phase 1: Planning and Preparation (6 – 12 Months)	6

Phase 2: Facility Design and Financing (3 – 12 Months)	7

Phase 3: Endorsement (0 – 1 Month)	8

Phase 4: Construction (12 – 30 Months)	8

Estimated Project Costs and Fees	9

Estimated Project Costs and Fees: Project Budget Snapshot	10

Partners in the Critical Access Hospital Replacement Project	11

# Introduction

Many of the more than 1300 Critical Access Hospitals (CAHs) in rural America were built in the 1940s and 1950s.  Over the past 60 years, communities have done renovations, expansions, and/or major rehabilitations - while about 100 have replaced their entire hospital.  Facility replacement may not be appropriate for all CAHs, but it is an option that should be considered for those with obsolete and/or worn-out infrastructure.

According to the 2008 Rural Hospital Replacement Facility Study1, hospital leadership continues to report improvement in tangible measures of hospital performance and operational efficiency after replacement.  Respondents also reported greater success in physician and staff recruitment and improved customer and employee satisfaction.  Additionally, the majority of replaced CAHs have documented that expenses are lower (on a unit cost basis) than pre-replacement.  Other intangible benefits include improved work culture, better quality of care and a significant boost to the local economy.

In an effort to facilitate the renovation processes for Critical Access Hospital’s who are very much in need of this support, the Department of Health and Human Services (HHS), Health Resources and Services Administration (HRSA), and the Office of Rural Health Policy (ORHP), is pleased to make this Critical Access Hospital Replacement Process: The Roadmap available to you, along with the more detailed Critical Access Hospital Replacement Process: The Manual.

Critical Access Hospital Replacement Process: The Roadmap provides a visual overview of the entire facility replacement process.  This process is divided into four chronological phases: (1) Planning, (2) Design and Financing, (3) Endorsement and (4) Construction.  Each phase is further described by: 1) events, 2), actions 3) duration, 4) costs/fees, and 5) involved parties. To help you manage your resources an estimate is provided for all project costs and fees.  Finally, a list of important project partners is provided.

The Roadmap provides a general timeline for all activities within each phase, although some actions will not apply to every project.   The replacement process will take 2 years or more to complete and you should strive to work on various actions simultaneously.  Timing is a huge

factor that impacts on finding capital and construction costs, thus care must be taken to ensure that actions are completed in a timely manner.

It is critical that the entire hospital leadership team, including the board of directors, is engaged in this process.  The board chair, executive committee, and board members, along with the CEO, CFO and COO, will have to provide visible and strong leadership throughout the entire process.   The hospital leadership team is critical to getting and keeping the project moving.

One of the first steps on your project schedule should be to find and hire the Full Project Coordination (FPC) resources (see page R12) that will help guide you through the entire facility replacement process, including development of your project schedule and work plan. The FPC resources represent you and coordinate the CAH facility replacement project. It’s critical that you work with them right from the beginning so that you understand your options.  You are not in this alone – your FPC resources can guide you through this process as they have guided other CAHs through successful facility replacement!

- 2008 Rural Hospital Replacement Facility Study, Eric Shell and Brian Haapala, Stroudwater Associates, sponsored by Stroudwater, Dougherty Company, and The Neenan Company

This roadmap is meant to provide an overview of the facility replacement process.  For more detailed guidance, see our companion document: CAH Replacement Process: The Manual.   Before you start, visit some replaced CAHs and talk to the people who took the lead in this process as well as hospital staff.  A list of these facilities is available in The Manual.

Good luck! We trust The Roadmap and The Manual will help guide you through a successful CAH replacement process.

# CAH Replacement Process Timeline

# Phase 1: Planning and Preparation (6 – 12 Months)

Full Project Coordination (FPC) resources should be found and hired to guide CAH through the replacement process.  First, CAH leadership needs to make a formal replacement decision based on the facilities assessment, debt capacity analysis, and market demand analysis.  Then, CAH leadership and FPC resources will start to work on: 1) financial feasibility and financing, 2) space programming, schematic design, and equipment and construction costs; 3) land acquisition; and 4) construction method.

| EVENTS | ACTIONS/ GOALS | DURATION | COSTS/FEES | INVOLVED PARTIES |
| --- | --- | --- | --- | --- |
| PROJECT ARTICULATION | Research and Hire FPC resources Commission Facilities Assessment Obtain Debt Capacity Analysis Obtain Market Demand Analysis Make Replacement Decision Approve Reimbursement Resolution Discuss Relocation with CMS Initiate CON Application Draft Programming/Space Plan | 1 – 6 months | FPC Resources Fee Facilities Assessment Fee Debt Capacity Analysis Fee Market Demand Analysis Fee | Project Sponsor FPC Resources Facilities Consultant CON Consultant State CON Office CMS State Office of Rural Health (SORH)/Flex Office State Health Facilities Finance Authority (HFFA) |
| FACILITY ASSESSMENT AND DESIGN | Complete Land Acquisition Perform Phase I Environmental (ESA) and Soils Studies Draft Schematic Design Perform Equipment Assessment Select Construction Method Finalize Project Budget | 3 – 6 months | Architect Fee Phase I ESA and Soils Study Fees Land Acquisition and Development Equipment Consultant Fee | Project Sponsor FPC Resources Architect Equipment Consultant Environmental Consultant |
| RESEARCH FINANCING AND ASSESS FEASIBILITY | Implement Financing Strategy Research Financing Options Commission Feasibility Study Prepare Financing Information | 3 – 6 months | Feasibility Study Fee | Project Sponsor FPC Resources State HFFA Lenders Fed Program Staff |
| COMMUNITY ENGAGEMENT AND CAPITAL CAMPAIGN | Develop and Implement Community Engagement Plan Develop and Implement Capital Campaign Plan | Ongoing | Campaign Consultant Fee Marketing and Development Costs | Project Sponsor Board FPC Resources Consultant Development Office SORH/Flex Office Rural Health Works Community |

# Phase 2: Facility Design and Financing (3 – 12 Months)

The feasibility study, completed in Phase I, is the basis for financing and requires financial, programmatic, and design information.  In a capital market financing, the CAH can obtain financing proposals from prospective lenders once there is a guaranteed maximum price (GMP). For Federal government enhancements (e.g., insurance, guarantee) and loans, the application must be approved prior to completing the financing process.

| EVENTS | ACTIONS/ GOALS | DURATION | COSTS/ FEES | INVOLVED PARTIES |
| --- | --- | --- | --- | --- |
| PROJECT ARTICULATION | Submit CON Application and Obtain Approval Continue Discussion with CMS | 1 – 6 months | CON Application Fee CON Consultant Fee | Project Sponsor FPC Resources CON Consultant State CON Office CMS SORH/Flex Office |
| DESIGN AND CONSTRUCTION DEVELOPMENT | Draft Design Development Drawings Refine Equipment Budget Draft Construction Documents/ Support Bid Process Obtain Guaranteed Maximum Price (GMP)/Signed Construction Agreement | 1 – 6 months | Architect Fee Equipment Consultant Fee | Project Sponsor FPC Resources Architect Construction Contractor Equipment Consultant |
| OBTAIN FINANCING | Capital Market Financing Obtain Financing Proposals from Prospective Underwriters/ Lenders Select Underwriter/Lender Engage Bond Counsel and Select Issuing Authority (if applicable) Government Programs and Loans Submit Application Obtain Approval | 1 - 9 months | Underwriter/ Lender Retainer Government Programs Government Program Application Fee (if applicable) | Project Sponsor FPC Resources State HFFA Capital Market Financing Underwriters/ Lenders Issuing Authority Bond Counsel Government Programs Program Staff (HUD or USDA) |
| COMMUNITY ENGAGEMENT AND CAPITAL CAMPAIGN | Continue Community Engagement Continue Capital Campaign | Ongoing | Marketing and Development Costs | Project Sponsor Board FPC Resources Campaign Consultant/ Development Office SORH/Flex Office Community |

# Phase 3: Endorsement (0 – 1 Month)

Phase 3 represents official acceptance of the loan/bond terms.  The responsibilities and duties of all parties are defined. Once the contract is signed and funding assured, construction can begin.

| EVENTS | ACTIONS/GOALS | DURATION | COSTS/FEES | INVOLED PARTIES |
| --- | --- | --- | --- | --- |
| LOAN OR BOND CLOSING AND ENDORSEMENT | Capital Market Financing Loan or Bond Closing Govt. Programs Receive Initial Funding and Okay to Construct | 0 – 1 month | Financing Costs (Attorney/Bond Counsel Fees and other processing fees) Initial Funds Disbursement Government Program Fee | Project Sponsor FPC Resources Attorneys Capital Market Issuing Authority Bond Counsel Lender Govt. Programs Lender Program Staff |
| BEGIN CONSTRUCTION | Complete Pre-Construction Begin Timely Groundbreaking | 0 – 1 month | Allowable Project Costs | Project Sponsor FPC Resources Lender/Federal Staff Construction Contractor Architect |
| COMMUNITY ENGAGEMENT AND CAPITAL CAMPAIGN | Continue Community Engagement Continue Capital Campaign | Ongoing | Marketing and Development Costs | Project Sponsor/Board FPC Resources Campaign Consultant/ Development Office SORH/Flex Office Community |

# Phase 4: Construction (12 – 30 Months)

In Phase 4, emphasis is placed on construction management and monitoring to ensure that the project is on schedule and within budget.  At project close, an attestation of project costs may be required and loan amortization begins.

| EVENTS | ACTIONS/ GOALS | DURATION | COSTS/FEES | INVOLVED PARTIES |
| --- | --- | --- | --- | --- |
| MONTHLY REQUISITIONS | Manage Timely Construction Progress Achieve Substantial Completion | 12 – 30 months (depending on contract terms) | Allowable Project Costs | Project Sponsor FPC Resources Construction Contractor Architect Lender/Fed Program Staff |
| PRE-CLOSING AND CONSTRUCTION COMPLETION | Perform Project Completion and Cost Certification | 0 – 1 month | Capitalized Interest during Construction Accountant Fees | Project Sponsor Construction Contractor Architect Accountant/CPA |
| FINAL LOAN CLOSING/ ENDORSEMENT | Final Closing/ Endorsement | 1 – 3 months | Attorney Fees Accountant Fees | Project Sponsor FPC Resources Lender/Fed.Program Staff Construction Contractor Attorney Accountant/CPA |
| COMMUNITY ENGAGEMENT AND CAPITAL CAMPAIGN | Implement Community Engagement Implement Capital Campaign | Ongoing | Marketing and Development Costs | Project Sponsor/Board Campaign Consultant/ Development Office SORH/Flex Office Community |

# Estimated Project Costs and Fees

A replacement project is a large investment.  Below are estimated project costs and fees based on a $25 million project ($22.5 million loan and $18.0 million construction component). A CAH may need to use cash reserves or operating funds to pay upfront costs prior to bond or loan closing.  Costs and fees are generally allowable costs and eligible for reimbursement at closing.  The FPC Resources will help the CAH negotiate favorable contracts for services.

Overall Project Cost Considerations

- Estimate total project cost at about 130-140 percent of the construction amount, which includes site costs.

- Additional costs other than construction include facility and equipment assessments, land acquisition, financing costs, and equipment and furnishings.

Phase 1: Planning/Preparation

- A Financial Advisor may work on contingency for a $10,000 - $25,000 retainer.

- Accounting firms perform a debt capacity analysis for $2,500 - $10,000.

- It is critical to know the environmental history, soil condition, flood plain designation, zoning and deed restrictions on a new land parcel prior to acquisition.  Remember, free land can have a huge cost!  Land acquisition and financing, if needed, may be costly and should be addressed as early as possible.

- The financial feasibility study may generally be obtained for $30,000 to $60,000 for a compilation and $50,000 to $90,000 for an examination.

Phase 2: Facility Design and Financing

- An architectural firm with CAH experience will charge between 6.5 and 7.5percent of construction costs. The standard American Institute Architects (AIA) contract calls for the total fee to be incurred (and payable) as follows: 1) Schematic Design 15percent; 2) Design Development 20 percent; 3) Construction Documents 40 percent; 4) Bidding         5 percent; and 5) Construction 20 percent - a total of 100 percent.

- If a Certificate of Need (CON) is required, the CON application fee may vary by state and be commensurate with project size.

- FHA Hospital Mortgage Insurance Application Fees: 80 basis points (bp) total, including 15 bp with application, 15 bp at loan commitment, and 50 bp at initial closing.  FHA program includes fixed rate funding for construction and permanent financing.

- USDA Guaranteed Loan Program has a 1 percent fee due at closing and no annual fee.  USDA program does not include construction financing.

Phase 3: Endorsement

- Financing fees are estimated at 3-4 percent of the loan with allocations of about 1-2 percent to the lender/underwriter, 0.5 percent to the financial advisor, and 1percent for attorneys (hospital attorney, bond counsel) and other fees.  Fee estimates fluctuate based on the financing vehicle (e.g., bond, mortgage) and whether the hospital is using a government enhancement program.

  - At loan or bond closing and initial fund disbursement, the hospital is reimbursed for allowable project costs made prior to closing (e.g., accounting services, land costs, CON fees).  Payments are generally made to FPC Resources, architect, construction management firm/contractor, and attorneys.

Phase 4: Construction

  - Allowable project costs are paid from loan proceeds as they are incurred.

- The interest during construction will vary based on financing method.  For loans, construction interest may be estimated at about half year of interest on the total loan.  Thus, for a $22.5 million loan at 7percent interest, the interest during construction is about $780,000 annually.  Bonds are issued at closing, however, so construction interest is accrued on the entire financed amount, or $1.57 million of interest annually.

# Estimated Project Costs and Fees: Project Budget Snapshot

$18 million construction project with total project cost of $25 million

This $25 million project is an estimate.  The financing is based on $2.5 million equity and $22.5 million financing.  Please note that the budget is not all-inclusive, in that this focuses on the actual replacement project.  Transition costs, including the Transition Planner, physical move to the new facility and initial operating capital are not addressed.

| Service | Estimated Costs/Fees | Comments |
| --- | --- | --- |
| Phase 1: Planning/Preparation |
| Full Project Coordination (FPC) Resources | $62,500 | Estimate .5-1 % of total project cost or $125,000 - $250,000; For this project budget, .5 % for the financial advisor is included in the estimated financing fees in phase 3 ($187,500 – 125,000 = $62,500) |
| Facilities Assessment | 5,000* | Facilities assessment ranges from $2,500 – $10,000 |
| Market Demand Analysis | 5,000 | Perform early in process to identify market potential |
| Debt Capacity Analysis | 5,000* | Analysis ranges from $5,000 – $10,000 |
| Architect Fee | 189,000 | Total architect fee estimated at 7% of construction cost. Phase 1: Schematic Design |
| Appraisal Fee | 5,000* | Applicable if hospital is using current property as an asset going into the loan; $5,000 – 10,000 May be included in financing costs |
| Equipment Assessment | 10,000 | For current inventory listing movable vs. sell or dispose Selection of new replacement equipment with specifications could increase fee up to $20,000 |
| Financial Feasibility Study | 50,000 | Feasibility study type based on financing requirements Compiled Forecast estimated at $30,000 - 60,000 Examined Forecast estimated at $50,000 - 90,000 |
| Phase I Environmental (ESA) and Soils Studies | 5,000 | Complete environmental and soils studies prior to land acquisition |
| Capital Campaign Consultant and/or Marketing/Development | 100,000 | Costs vary for marketing and development based on the level of community engagement or capital campaign Estimate is based on 10% of $1 million campaign goal |
| Land Acquisition Costs | Varies | Costs vary widely and land donations are encouraged Land acquisition should be addressed early due to land and site development costs and financing, if needed |
| Phase 1 Total | $421,500 | Total does not include the estimated costs noted with * as the service may be included in the FPC Resources Fee |
| Phase 2: Facility Design and Financing |
| Architect Fee | 819,000 | Phase 2: Design Development, Construction Documents, Bidding |
| CON Application Fee | Varies | Varies by State; commensurate with project size |
| Phase 2 Total | $819,000 |  |
| Phase 3: Endorsement |
| Initial Funds Disbursement | -- | Hospital is reimbursed for allowable project costs made prior to closing (costs for phases 1 and 2) |
| Financing costs | 700,000 | Estimate 3-4% of amount financed |
| Owner’s Contingency Fund | 900,000 | 5% of construction cost to fund unforeseen items |
| Phase 3 Total | $1,600,000 |  |
| Phase 4: Construction |
| Construction and Site Development (Allowable project costs) | 18,000,000 | 60,000 sq. ft. @ $300/sq.ft. Subject to regional adjustment Includes contractor's fee and general conditions |
| Equipment and Furnishings | 3,600,000 | Estimate 20% of Construction amount |
| Architect Fee | 252,000 | For services provided during construction |
| Capitalized interest during construction | 780,000 | Estimate per each 12 months of construction; based on 7percent on $22.5 million loan |
| Phase 4 Total | $22,627,000 |  |
| Estimated Project Cost | $25,477,500 |  |

* Service/fee may be included in FPC Resources Fee

# Partners in the CAH Replacement Project

A replacement project requires the right expertise, guidance, and support.  A CEO simply cannot do this alone!  Hospital leadership (board and administration) must plan to commit a significant amount of time to the replacement project.

Please note that the “Involved Parties” column for each phase specifically lists the Project Sponsor for each event.  The designated Project Sponsor may be represented by board chair, board member, hospital administrators (e.g., CEO, CFO, COO), or community leaders.  The Project Sponsor, Board Chair, CEO and CFO should be engaged throughout the process.  The hospital may hire FPC Resources to represent the hospital’s interests and guide the project throughout the entire process; however, hospital leadership is still responsible for making decisions.

|  | The replacement process is completed during normal hospital operations. So hospital operations must continue at the same level or higher as this will impact hospital finances and financial feasibility. Hospitals are generally considered one of the most complex facilities to design and build, which is why it is important to have design and construction professionals with hospital experience, especially with CAHs. This is a collaborative effort and it is critical to have key project team members that can work well together as partners. Get recommendations and interview several FPC Resources, architects, contractors, and hire the team that works best with you and your community. |
| --- | --- |

|  | Partners in the CAH Replacement Project The team members you select will greatly impact the cost, timeframe and success of your project. Choose them wisely by doing research and talking to others, especially CAHs that have completed this process. Your CAH Replacement Project Team should include: *Project Sponsor/Hospital Leadership Team *Full Project Coordination Resources *Lender(s) *Architect *Construction Contractor/Construction Management Firm Equipment Consultant Environmental Consultant HUD and USDA staff Financial Feasibility Consultant Capital Campaign Consultant Attorneys/Bond Counsel Issuing Authority Medicare Reimbursement (Billing) Consultant and/or A/R Collections Consultant CON Consultant * These are key project team members who will be involved throughout the project. Early collaboration between the project team, particularly the FPC Resources, architect and construction contractor, is recommended. Some important resources for the Hospital Leadership Team may include: State Office of Rural Health (SORH)/Flex Office State Health Facilities Finance Authorities |
| --- | --- |

- Full Project Coordination (FPC) Resources is highly recommended.  Members of the FPC resources serve as the hospital’s advocate throughout the replacement project.  The FPC resources must come together at the beginning of the process to coordinate the project and provide unbiased expertise, guidance, and support to facilitate decision-making and action.  The FPC resources facilitate decision-making by clearly laying out the hospital’s options as well as the most efficient and cost-effective ways to keep the project moving.

FPC resources are needed for 3 project functions and have these areas of expertise:

- Financing Guidance: The hospital should be represented by a qualified financial advisor who will act on its behalf.  A Financial Advisor helps the hospital navigate the financing process, which may include board education, exploring financing options, performing debt capacity analysis and financial feasibility, and facilitating interaction with lenders and/or Federal enhancement programs.

- Programming and Space Planning: Programming and space planning support strategic use of space to meet community needs and maximize hospital revenue.  This role may be performed by an Architect, Facilities Planner, Owner Advocate, Owner’s Representative or Project Manager.

- Management of Design and Construction: An Owner Advocate, Owner’s Representative, Project Manager, or Construction Consultant provides guidance to the hospital and represents the owner’s interests during the design and construction process.

- Architect is required to design the CAH with the appropriate range of services. The architect should have CAH experience and must be licensed in the State where the project is located. The debt capacity analysis and programming and space plan should be done before starting the architectural design.

- Construction Contractor should have CAH experience and is responsible for ensuring a fully functional construction project for the price agreed upon in the construction contract.

- Federal Program Staff include representatives of Federal credit enhancement programs that may facilitate access to capital, including HUD’s Hospital Mortgage Insurance and USDA’s Guaranteed and Direct Loan Programs.

- State Office of Rural Health (SORH)/Flex Office has been instrumental in CAH replacements by providing information and support related to economic impact, community engagement, financial feasibility studies, CON application/waiver, financing resources, and working with the CMS Regional Office regarding continued CAH designation.

- State Health Facilities Finance Authorities (HFFAs) are State capital financing resources for hospitals and health care facilities.

Public Domain Notice

All material appearing in this document is in the public domain and may be reproduced without permission from HRSA.  Citation of the source is appreciated.

Recommended Citation

Critical Access Hospital Replacement Process: The Roadmap, U.S. Department of Health and Human Services (2010), Health Resources and Services Administration, Office of Rural Health Policy, Rockville, MD 20857

Cover Photo Credit: Dan / FreeDigitalPhotos.net

This document is available online at http://www.ruralhealth.hrsa.gov/

Document

This document was prepared for United States Department of Health and Human Services, Health Resources and Services Administration, Office of Rural Health Policy, under contract #06-N250-5519 the by Phineas Consulting, LLC.

# Footnotes

If you utilize FPC Resources, their fees will be payable throughout the project based on services provided.

Certificate of Need (CON) requirements may not be applicable as all states do not have CON.

Financing options should be evaluated with input from an independent Financial Advisor (FPC Resources).

Federal Program Staff are only involved if a government enhancement or loan program is utilized.

Community engagement and/or capital campaign should begin prior to and continue throughout the project.  Capital campaign funds raised prior to the loan closing can favorably impact the loan amount.

There is a general process for capital market financing; however, if a government enhancement program (HUD or USDA) is used, there are additional requirements that must be met that could increase the financing timeframe an additional 3 to 6 months.