## Budget Worksheet
ICD-10 Budget Estimator
|  |  | 2014 |  |  | 2015 Cost
Cost Categories | Projected Effort (Hrs) | Projected Cost ($) | Q2 2014 | Q3 2014 | Q4 2014 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Risks and Assumptions
Project Manager | 960 | 64000 | 22000 | 22000 | 10000 | 10000 | 0 | 0 | 0 | Decision to leverage external consulting at 100/hr to support internal project manager
Physician Education | 230 | 28000 | 16000 | 4000 | 8000 |  |  |  |  | Decision to use XYZ vendor to provide Physician Education. Cost are estimated based upon proposal
Coders - I/P | 3120 | 81120 |  | 13520 | 13520 | 13520 | 13520 | 13520 | 13520 | A new I/P Coder will be hired starting Q3 2014 to support parallel coding; the cost through CY 2015 will be captured in the ICD-10 budget per CFO
Clinical Documentation Specialists | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tracking the effort for 3 CDIS to attend training anticipated at 60 hour per FTE
Hardware |  | 0 | [7 empty] | EMR Vendor indicated that additional servers are required during upgrade; one time HW charge
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| 4490 | 173120 | 38000 | 39520 | 31520 | 23520 | 13520 | 13520 | 13520

## Cost Categories
Use this tab to list all your cost categories for your implementation
Consulting Services
Project Manager
Technical Staff
Functional Staff
Executives
Physician Education
Clinical Documentation Specialists
Post Implementation Support
Coders - I/P
Coders - O/P
Coders - Profee
Productivity Loss
Fixed Costs
Others
Travel
Hardware
Software