## Sheet1
Communication event | Audience | Timing | Frequency | Vehicle | Purpose | Creator (w/Subject Matter expert support) | Sender
Project team kick-off | ICD-10 workstream leads | Project Start | Weekly | Weekly status meeting | Project status Issue and risk management | ICD-10 PMO | Project director
Project status updates to Steering Committee | Operations leadership team | Project Start | Monthly | Operations meeting | Project status Key decisions Requests for assistance | ICD-10 PMO | Project sponsor
General awareness | Employees, Physicians, Contractors | Project Start | Quarterly | Various – electronic and verbal | Case for change Answer key questions Dedicated CareLine area | ICD-10 communications team | Project sponsor
General staff and physicians | General staff, Physicians (employed and private practice) | Project Start | Quarterly | Various – electronic and verbal | Inform leaders of project timeline and milestones. Physician outreach Ongoing training | ICD-10 communications team | Designated physician sponsor
Department/Function | Impacted department/function | Project Start +3 months | Monthly | Various – electronic and verbal (at group level) | Reinforce central communications messages Dept impact/change Physician outreach | ICD-10 communications team | Designated department or physician sponsor
Job/role | Impacted job/role | Project Start +3 months | Will vary based on stakeholder and potential process re-engineering activities | Various – electronic and verbal (individual level) | Reinforce central communications messages Job impact/change Tactical changes/training schedule/reminders | ICD-10 communications team | Department leader/manager/
Transition week | All impacted stakeholders | T – 1 week | One-time event | Electronic | Set expectations, reminders | ICD-10 communications team | Project sponsor
Transition day | All impacted stakeholders | T | One-time event | Electronic | Go-live announcement Reminders on source of help/escalation | ICD-10 communications team | Project sponsor
Post-transition | All impacted stakeholders | T + 1 week | Regular monitoring for 6 months | Electronic | Update on progress Lessons learned Track key metrics | ICD-10 communications team | Project sponsor
Vendor/business partner/payer communications | Vendors/business partners/payers/clearinghouses | Project Start | Every other month | Electronic and verbal (individual level) | Set expectations Monitor readiness | ICD-10 communications team | Current liaison + ICD-10 project team